## PMPS LIST FY 2023-24_FOR AUDIT
INSTRUMENTATION PMPS LIST RED AREA-I (02/03 AREA)
FY- 2023-24 ( START ON 01.04.2023 )
S.NO | AREA | TAG NO | EQUIPMENT DESCRIPTION | ACTI VITY | ACCURACY% | Frequency | SCH. WEEK | Critciality | WI.NO | PMPS DONE ON | NEXT PMPS DUE
1 | DILLUTION | 03LT135 | MUD TK-34 LEVEL TXR | FCK |  | 52 | 1 | E | 29 | 03.04.23 | 03.04.24
2 | DILLUTION | 03LT710A/ B | DILUTION TANK 718A/ B LEVEL | FCK |  | 52 | 1 | E | 29 | 03.04.23 | 03.04.24
3 | DESILICATION | 03FT121 | PH-I DESILICATION STEAM FLOW | CAL | 2 | 52 | 1 |  | 11 | 04.04.23 | 04.04.24
4 | HRD/DCW | 04LI1403C | DCW-1 SURFACE LIQUOR LEVEL | FCK |  | 52 | 1 | E | 29 | 04.04.23 | 04.04.24
5 | BALL MILL | 02FCV515 | MAIN SL FLOW C/V TO BM003 | CAL | 5 | 52 | 1 |  | 12 | 06.04.23 | 06.04.24
6 | BALL MILL | 02FT518 | FE SL FLOW TO BM003 | FCK |  | 52 | 1 |  | 55 | 06.04.23 | 06.04.24
7 | BALL MILL | 02PI1122 | BM1001 COMPRESSOR AIR RECEIVER TK PRESSURE | CAL | 1 | 52 | 1 |  | 11 | 08.04.23 | 08.04.24
8 | BALL MILL | 02PI1127 | BM1001 DISCHARGE PRESSURE FOR CLUTCH(AFTER SOV) | CAL | 1 | 52 | 1 |  | 11 | 08.04.23 | 08.04.24
9 | BALL MILL | 02PI1222 | BM1002 COMPRESSOR AIR RECEIVER TK PRESSURE | CAL | 1 | 52 | 2 |  | 11 | 10.04.23 | 10.04.24
10 | BALL MILL | 02PI1227 | BM1002 DISCHARGE PRESSURE FOR CLUTCH(AFTER SOV) | CAL | 1 | 52 | 2 |  | 11 | 10.04.23 | 10.04.24
11 | PD AREA | 02LT510 | PRE-DESILICATION TK 510 LEVEL | FCK |  | 52 | 2 | E | 29 | 12.04.23 | 12.04.24
12 | DESILICATION | 03PT707 | PH-III DESILICATION STEAM HEADER PRESSURE | CAL | 1 | 52 | 2 |  | 11 | 12.04.23 | 12.04.24
13 | DESILICATION | 03TT708A | DESILICATION TANK 724 O/L TEMPERATURE | FCK |  | 52 | 2 |  | 44 | 13.04.23 | 13.04.24
14 | HRD/DCW | 04WI1403 | DCW-1 RAKE TORQUE | FCK |  | 52 | 2 |  | 58 | 13.04.23 | 13.04.24
15 | EFFLUENT | 36PHI01 | UP STREAM PH INDICATOR | CAL | 1 | 52 | 2 |  | 64 | 15.04.23 | 15.04.24
16 | EFFLUENT | 36PHI02 | DOWN STREAM PH INDICATOR | CAL | 1 | 52 | 2 |  | 64 | 15.04.23 | 15.04.24
17 | EFFLUENT | 36PHT01 | UP STRM PH TRANSMITR | CAL | 1 | 52 | 3 | E | 20 | 17.04.23 | 17.04.24
18 | EFFLUENT | 36PHT02 | DOWN STRM PH TRANS | CAL | 1 | 52 | 3 | E | 20 | 17.04.23 | 17.04.24
19 | BALL MILL | 02LT 708 | BM701 BUXITE SILO-701 LEVEL | FCK |  | 52 | 3 |  | 29 | 19.04.23 | 19.04.24
20 | BALL MILL | 02TT853 | BM701 DE BEARING TEMPERATURE | FCK |  | 52 | 3 |  | 44 | 19.04.23 | 19.04.24
21 | STACKER | 02WI001 | OLD STACKER/STACKER 01 BELT WEIGHER | CAL | 2 | 52 | 3 |  | 4 | 20.04.23 | 20.04.24
22 | DIGESTION | 03FI101A | PH-1 DIGESTION 2ND STATION STEAM FLOW | CAL | 1 | 52 | 3 |  | 11 | 20.04.23 | 20.04.24
23 | DIGESTION | 03FI102A | PH-2 DIGESTION 2ND STATION STEAM FLOW | CAL | 1 | 52 | 3 |  | 11 | 22.04.23 | 22.04.24
24 | DILLUTION | 03LT712 | PH-3 MUD DISPOSAL TANK 717A LEVEL | FCK |  | 52 | 3 | E | 29 | 22.04.23 | 22.04.24
25 | HRD/DCW | 04LI1404C | DCW-2 SURFACE LIQUOR LEVEL | FCK |  | 52 | 4 | E | 29 | 24.04.23 | 24.04.24
26 | HRD/DCW | 04LSW1425 | DCW-1/2 SUMP PUMP LSW | FCK |  | 52 | 4 | E | 31 | 24.04.23 | 24.04.24
27 | HRD/DCW | 04WI1404 | DCW-2 RAKE TORQUE | FCK |  | 52 | 4 |  | 58 | 26.04.23 | 26.04.24
28 | TTD | 04LT982 | CYTEC PREPARATION TANK 982 LEVEL | CAL | 1 | 52 | 4 | E | 14 | 26.04.23 | 26.04.24
29 | DIGESTION | 03CT102 | PH-II DIGESTION RC POT-002 CONDUCTIVITY | FCK |  | 52 | 4 |  | 36 | 27.04.23 | 27.04.24
30 | DIGESTION | 03CT501 | PH-I DIGESTION RC POT-501 CONDUCTIVITY | FCK |  | 52 | 4 |  | 36 | 27.04.23 | 27.04.24
31 | DIGESTION | 03CT502 | PH-II DIGESTION RC POT-502 CONDUCTIVITY | FCK |  | 52 | 4 |  | 36 | 29.04.23 | 29.04.24
32 | DIGESTION | 03LSW25 | SUMP TANK LEVEL SWITCH DIGESTION | FCK |  | 52 | 4 | E | 31 | 29.04.23 | 29.04.24
33 | DILLUTION | 03LT507 | DILUTION TK-36 LEVEL TXR | FCK |  | 52 | 5 | E | 29 | 02.05.23 | 02.05.24
34 | DESILICATION | 03CT122 | PH-II DESILICATION RC CONDUCTIVITY | FCK |  | 52 | 5 |  | 36 | 02.05.23 | 02.05.24
35 | DESILICATION | 03FT707 | PH-III DESILICATION STEAM FLOW | CAL | 2 | 52 | 5 |  | 11 | 04.05.23 | 04.05.24
36 | DESILICATION | 03LT124 | PH-II DESILICATION RC POT LEVEL | CAL | 2 | 52 | 5 |  | 14 | 04.05.23 | 04.05.24
37 | DESILICATION | 03PT708 | PH-III DESILICATION STEAM INTERNAL PRESSURE | CAL | 1 | 52 | 5 |  | 11 | 05.05.23 | 05.05.24
38 | BALL MILL | 02TT005-7 | BM-005 NDE MOTOR BEARING TEMP. TXR. | FCK |  | 52 | 5 |  | 44 | 06.05.23 | 06.05.24
39 | BALL MILL | 02TT005-8 | BM-005 DE MOTOR BEARING TEMP. TXR. | FCK |  | 52 | 5 |  | 44 | 06.05.23 | 06.05.24
40 | BALL MILL | 02BW503 | BM005 BELT WEIGHER | CAL | 2 | 52 | 6 |  | 4 | 08.05.23 | 08.05.24
41 | DIGESTION | 03LT104 | PH-II DIGESTION POT-002 LEVEL | CAL | 2 | 52 | 6 | E | 14 | 08.05.23 | 08.05.24
42 | DILLUTION | 03LT131 | WATER STORAGE TK-39 LEVEL | CAL | 1 | 52 | 6 | E | 14 | 10.05.23 | 10.05.24
43 | HRD/DCW | 04LI1405C | DCW-3 SURFACE LIQUOR LEVEL | FCK |  | 52 | 6 | E | 29 | 10.05.23 | 10.05.24
44 | DIGESTION | 03PCV102 | PRESSURE CONTROL VALVE TK-16/17 | CAL | 5 | 52 | 6 |  | 12 | 11.05.23 | 11.05.24
45 | DIGESTION | 03PCV501 | PRESSURE CONTROL VALVE TK-18/19 | CAL | 5 | 52 | 6 |  | 12 | 11.05.23 | 11.05.24
46 | DESILICATION | 03CT703 | PH-III DESILICATION RC CONDUCTIVITY | FCK |  | 52 | 6 |  | 36 | 13.05.23 | 13.05.24
47 | DESILICATION | 03LT705/ 706 | DESILICATION TANK 727/ 728 LEVEL | FCK |  | 52 | 6 | E | 29 | 13.05.23 | 13.05.24
48 | DESILICATION | 03LT707 | DESILICATION CONDENSATE POT 703 LEVEL | CAL | 2 | 52 | 7 | E | 14 | 15.05.23 | 15.05.24
49 | HRD/DCW | 04WI1405 | DCW-3 RAKE TORQUE | FCK |  | 52 | 7 |  | 58 | 15.05.23 | 15.05.24
50 | BALL MILL | 02PI004 | BM-004 GEAR BOX LUB OIL PR.TXR | CAL | 1 | 52 | 7 |  | 11 | 17.05.23 | 17.05.24
51 | BALL MILL | 02TT878 | BM701 BEARING LUBRICATION OIL RESERVOIR TEMP | FCK |  | 52 | 7 |  | 44 | 17.05.23 | 17.05.24
52 | DESILICATION | 03LCV707 | DESILICATION RC POT LEVEL CONTROL VALVE | CAL | 5 | 52 | 7 |  | 12 | 18.05.23 | 18.05.24
53 | DESILICATION | 03PCV708 | DESILICATION STEAM FLOW CONTROL VALVE | CAL | 5 | 52 | 7 |  | 12 | 18.05.23 | 18.05.24
54 | DESILICATION | 03PT130 | PH-II DESILICATION INTERNAL PRESSURE | CAL | 1 | 52 | 7 |  | 11 | 19.05.23 | 19.05.24
55 | DESILICATION | 03TT128A | PH-II DESILICATION TK-46 TEMPERATURE | FCK |  | 52 | 8 |  | 44 | 22.05.23 | 22.05.24
56 | DESILICATION | 03TT128B | PH-II DESILICATION TK-47 TEMPERATURE | FCK |  | 52 | 8 |  | 44 | 22.05.23 | 22.05.24
57 | HRD/DCW | 04LI1406C | DCW-4 SURFACE LIQUOR LEVEL | FCK |  | 52 | 8 | E | 29 | 24.05.23 | 24.05.24
58 | HRD/DCW | 04WI1406 | DCW-4 RAKE TORQUE | FCK |  | 52 | 8 |  | 58 | 24.05.23 | 24.05.24
59 | TTD | 04LT983 | CYTEC SOLUTION TANK 983 LEVEL | CAL | 1 | 52 | 8 | E | 14 | 25.05.23 | 25.05.24
60 | TTD | 04LT984 | TTD CYTEC DILLUTION WATER TANK 984 LEVEL | CAL | 1 | 52 | 8 | E | 14 | 25.05.23 | 25.05.24
61 | LIME | 56LT101/ 102 | TK-236/ 237 LVL TXR | FCK |  | 52 | 8 | E | 29 | 26.05.23 | 26.05.24
62 | BALL MILL | 02TT850 | BM701 FE BEARING TEMPERATURE | FCK |  | 52 | 8 |  | 44 | 26.05.23 | 26.05.24
63 | CRUSHER | 01ZSS701 | CRUSHER-701 SPEED SWITCH | FCK |  |  | 8 |  | 68 | 27.05.23 | 27.05.24
64 | CRUSHER | 01VSZSS701 | CRUSHER-701 VIBRATING SCREEN SPEED SWITCH | FCK |  |  | 9 |  | 68 | 29.05.23 | 29.05.24
65 | CRUSHER | 01VSZSS1001 | CRUSHER-1001 VIBRATING SCREEN SPEED SWITCH | FCK |  |  | 9 |  | 68 | 29.05.23 | 29.05.24
66 | HRD/DCW | 04LSW1426 | DCW-4 SUMP PUMP LSW | FCK |  | 52 | 9 | E | 31 | 31.05.23 | 31.05.24
67 | CRUSHER | 01TSW701 | CRUSHER 701 HYDRO COUPLER TEMP SWITCH | FCK |  | 52 | 9 |  | 67 | 31.05.23 | 31.05.24
68 | BALL MILL | 02TT851 | BM701 DE BEARING TEMPERATURE | FCK |  | 52 | 9 |  | 44 | 01.06.23 | 01.06.24
69 | PD AREA | 02LI1004A /B | PD HEATING TANK 1004A/ B LEVEL | FCK |  | 52 | 9 | E | 29 | 03.06.23 | 03.06.24
70 | PD AREA | 02LT505 | PRE-DESILICATION TK 505 LEVEL | FCK |  | 52 | 9 | E | 29 | 03.06.23 | 03.06.24
71 | DIGESTION | 03TT265 | PH-I DIGESTION TANK 20/265 O/L TEMP TXR | FCK |  | 52 | 10 |  | 44 | 05.06.23 | 05.06.24
72 | DILLUTION | 03LSW99 | SUMP TANK LEVEL SWITCH DILUTION | FCK |  | 52 | 10 | E | 31 | 05.06.23 | 05.06.24
73 | SETTLER | 04LSW915 | SUMP TANK-808 LEVEL SWITCH SETTLER | FCK |  | 52 | 10 | E | 31 | 07.06.23 | 07.06.24
74 | SETTLER | 04LSW916 | SUMP TANK-807 LEVEL SWITCH SETTLER | FCK |  | 52 | 10 | E | 31 | 07.06.23 | 07.06.24
75 | TTD | 04LT961 | TTD O/F TANK-961 LEVEL TRANSMITTER | CAL | 1 | 52 | 10 | E | 11 | 09.06.23 | 09.06.24
76 | TTD | 04LT962 | TTD O/F TANK-962 LEVEL TRANSMITTER | CAL | 1 | 52 | 10 | E | 11 | 09.06.23 | 09.06.24
77 | TTD | 04LSW917 | SUMP TANK-821 LEVEL SWITCH TTD | FCK |  | 52 | 10 | E | 31 | 10.06.23 | 10.06.24
78 | BALL MILL | 02TI1161 | BM-1001 OIL RESERVOIRTEMPARATURE | FCK |  | 52 | 11 |  | 44 | 12.06.23 | 12.06.24
79 | BALL MILL | 02TI1261 | BM-1002 OIL RESERVOIRTEMPARATURE | FCK |  | 52 | 11 |  | 44 | 12.06.23 | 12.06.24
80 | PD AREA | 02LT507 | PRE-DESILICATION TK 507 LEVEL | FCK |  | 52 | 11 | E | 29 | 13.06.23 | 13.06.24
81 | DESILICATION | 03FT127 | PH-II DESILICATION STEAM FLOW | CAL | 2 | 52 | 11 |  | 11 | 13.06.23 | 13.06.24
82 | SETTLER | 04XT904 | SETTLER 904 RAKE TORQUE | FCK |  | 52 | 11 |  | 57 | 15.06.23 | 15.06.24
83 | BALL MILL | 02TT003-7 | NDE MOTOR BEARING TEMP. TXR. | FCK |  | 52 | 11 |  | 44 | 15.06.23 | 15.06.24
84 | BALL MILL | 02TT003-8 | DE MOTOR BEARING TEMP. TXR. | FCK |  | 52 | 11 |  | 44 | 17.06.23 | 17.06.24
85 | LIME | 56LSW215 | LIME LVL SWITCH SUMP | FCK |  | 52 | 11 | E | 31 | 17.06.23 | 17.06.24
86 | EFFLUENT | 36LSW101 | LEV SW SUMP EFFL.PON | FCK |  | 52 | 12 | E | 31 | 19.06.23 | 19.06.24
87 | EFFLUENT | 36LSW102 | LEV SW SUMP EFFL.PON | FCK |  | 52 | 12 | E | 31 | 19.06.23 | 19.06.24
88 | DESILICATION | 03PT122 | PH-I DESILICATION INTERNAL PRESSURE | CAL | 1 | 52 | 12 |  | 11 | 21.06.23 | 21.06.24
89 | DESILICATION | 03TT122A | PH-I DESILICATION TK-41 TEMPERATURE | FCK |  | 52 | 12 |  | 44 | 21.06.23 | 21.06.24
90 | DESILICATION | 03TT122B | PH-I DESILICATION TK-42 TEMPERATURE | FCK |  | 52 | 12 |  | 44 | 22.06.23 | 22.06.24
91 | DILLUTION | 03LT134 | MUD TK-33 LEVEL TXR | FCK | 1 | 52 | 12 | E | 29 | 23.06.23 | 23.06.24
92 | LIME | 56WT102 | CONV-68 WEIGHT TXR | CAL | 2 | 52 | 12 |  | 4 | 23.06.23 | 23.06.24
93 | CRUSHER | 01TT001 | CRUSHER-001 GEAR BOX OIL TEMP TXR | FCK |  | 52 | 13 |  | 44 | 26.06.23 | 26.06.24
94 | SETTLER | 04XT905 | SETTLER 905 RAKE TORQUE | FCK |  | 52 | 13 |  | 57 | 26.06.23 | 26.06.24
95 | CRUSHER | 01FS001 | CRUSHER-1 OIL FLOW SWITCH | FCK |  | 52 | 13 |  | 37 | 27.06.23 | 27.06.24
96 | CRUSHER | 01FS002 | CRUSHER-2 OIL FLOW SWITCH | FCK |  | 52 | 13 |  | 37 | 27.06.23 | 27.06.24
97 | CRUSHER | 01TT002 | CRUSHER-002 GEAR BOX OIL TEMP TXR | FCK |  | 52 | 13 |  | 44 | 28.06.23 | 28.06.24
98 | CRUSHER | 01ZSS001 | CRUSHER-1 SPEED SWITCH | FCK |  | 52 | 13 |  | 68 | 28.06.23 | 28.06.24
99 | BALL MILL | 02TT807 | BM-701 MOTOR NDE BRNG. TEMP.TXR | FCK |  | 52 | 13 |  | 44 | 30.06.23 | 30.06.24
100 | BALL MILL | 02TT808 | BM-701 MOTOR DE BRNG. TEMP.TXR | FCK |  | 52 | 14 |  | 44 | 03.07.23 | 03.07.24
101 | PD AREA | 02LT506 | PRE-DESILICATION TK 506 LEVEL | FCK |  | 52 | 14 | E | 29 | 03.07.23 | 03.07.24
102 | DIGESTION | 03CT101 | PH-I DIGESTION RC POT-001 CONDUCTIVITY | FCK |  | 52 | 14 |  | 36 | 05.07.23 | 05.07.24
103 | RECLAIMER | 52FS001 | RECLAIMER OIL FLOW SWITCH | FCK |  | 52 | 14 |  | 37 | 05.07.23 | 05.07.24
104 | RECLAIMER | 52PS701 | PR. LINE FILTER PR. SWITCH | FCK |  | 52 | 14 |  | 37 | 06.07.23 | 06.07.24
105 | RECLAIMER | 52FPS702 | SUCTION FILTER PR. SWITCH | FCK |  | 52 | 14 |  | 37 | 06.07.23 | 06.07.24
106 | STACKER | 52LS001 | STACKER LEVEL SWITCH | FCK |  | 52 | 14 |  | 37 | 08.07.23 | 08.07.24
107 | CRUSHER | 01ZSS002 | CRUSHER-2 SPEED SWITCH | FCK |  | 52 | 14 |  | 68 | 08.07.23 | 08.07.24
108 | CRUSHER | 01ZSS003 | VS-1 SPEED SWITCH | FCK |  | 52 | 15 |  | 68 | 10.07.23 | 10.07.24
109 | CRUSHER | 01ZSS004 | VS-2 SPEED SWITCH | FCK |  | 52 | 15 |  | 68 | 10.07.23 | 10.07.24
110 | DIGESTION | 03FT101 | PH-I DIGESTION STEAM FLOW | CAL | 2 | 52 | 15 |  | 11 | 12.07.23 | 12.07.24
111 | DIGESTION | 03LT102 | PH-I DIGESTION COND POT-001 LEVEL | CAL | 2 | 52 | 15 |  | 14 | 12.07.23 | 12.07.24
112 | DIGESTION | 03TT266 | PH-I DIGESTION TANK 25/266 O/L TEMP TXR | FCK |  | 52 | 15 |  | 44 | 14.07.23 | 14.07.24
113 | DIGESTION | 03PI1017A | PUMP 1017A H/C OIL PRESSURE | CAL | 1 | 52 | 15 |  | 11 | 14.07.23 | 14.07.24
114 | RECLAIMER | 52LS703 | SUCTION VALVE LIMIT SWITCH | FCK |  | 52 | 15 |  | 37 | 15.07.23 | 15.07.24
115 | RECLAIMER | 52LS705 | FLOAT SWITCH | FCK |  | 52 | 16 |  | 37 | 17.07.23 | 17.07.24
116 | RECLAIMER | 52PS704 | PR. SWITCH | FCK |  | 52 | 16 |  | 37 | 17.07.23 | 17.07.24
117 | DIGESTION | 03TT509 | PH-II DIGESTION TANK 25 O/L TEMPARATURE | FCK |  | 52 | 16 |  | 44 | 19.07.23 | 19.07.24
118 | GEHO | 11PI1804L | PROPELLING LIQUID PR. TXR | CAL |  | 52 | 16 |  | 8 | 19.07.23 | 19.07.24
119 | GEHO | 11PI1805 | AIR PR. TXR | CAL | 1 | 52 | 16 |  | 8 | 21.07.23 | 21.07.24
120 | DIGESTION | 03TT510 | PH-II DIGESTION TANK 20 O/L TEMPARATURE | FCK |  | 52 | 16 |  | 44 | 21.07.23 | 21.07.24
121 | DESILICATION | 03CT121 | PH-I DESILICATION RC CONDUCTIVITY | FCK |  | 52 | 16 |  | 36 | 22.07.23 | 22.07.24
122 | DESILICATION | 03LT122 | PH-I DESILICATION RC POT LEVEL | CAL | 2 | 52 | 17 |  | 14 | 24.07.23 | 24.07.24
123 | SETTLER | 04LT920 | SODIC CONDENSATE TANK 970 LEVEL | CAL | 2 | 52 | 17 | E | 14 | 24.07.23 | 24.07.24
124 | SETTLER | 04LT923 | SODIC CONDENSATE TANK 971 LEVEL | CAL | 2 | 52 | 17 | E | 14 | 26.07.23 | 26.07.24
125 | SETTLER | 04LT925 | THIRD WASHER O/F TANK 973 LEVEL | CAL | 2 | 52 | 17 | E | 14 | 26.07.23 | 26.07.24
126 | SETTLER | 04LT926 | THIRD WASHER O/F TANK 972 LEVEL | CAL | 2 | 52 | 17 | E | 14 | 27.07.23 | 27.07.24
127 | GEHO | 11PI1803 | SUCTION AIR VESSEL PR. TXR | CAL | 1 | 52 | 17 |  | 11 | 27.07.23 | 27.07.24
128 | GEHO | 11PI1806 | GEHO PUMP DISCHARGE PR. TXR-1 | CAL |  | 52 | 17 |  | 11 | 28.07.23 | 28.07.24
129 | BALL MILL | 02TT004-7 | NDE MOTOR BEARING TEMP. TXR. | FCK |  | 52 | 17 |  | 44 | 28.07.23 | 28.07.24
130 | BALL MILL | 02TT004-8 | DE MOTOR BEARING TEMP. TXR. | FCK |  | 52 | 18 |  | 44 | 31.07.23 | 31.07.24
131 | PD AREA | 02TT703 | PDS TK-702 SLURRY TEMPREATURE | FCK |  | 52 | 18 |  | 44 | 31.07.23 | 31.07.24
132 | PD AREA | 02TT704 | PDS TK-703 SLURRY TEMPREATURE | FCK |  | 52 | 18 |  | 44 | 02.08.23 | 02.08.24
133 | HRD/DCW | 04LI1418 | FRESH CAUSTIC TANK LEVEL | FCK |  | 52 | 18 | E | 29 | 02.08.23 | 02.08.24
134 | GEHO | 11LSW1808 | NEW GEHO SUMP PUMP LSW | FCK |  | 52 | 18 | E | 31 | 04.08.23 | 04.08.24
135 | BALL MILL | 02LSW709 | SUMP TANK-801 LEVEL SWITCH BM-701 | FCK |  | 52 | 18 | E | 31 | 04.08.23 | 04.08.24
136 | BALL MILL | 02BW501 | BM003 BELT WEIGHER | CAL | 2 | 52 | 18 |  | 4 | 05.08.23 | 05.08.24
137 | PD AREA | 02LSW551 | SUMP TANK-551 LEVEL SWITCH PDS | FCK |  | 52 | 18 | E | 31 | 05.08.23 | 05.08.24
138 | PD AREA | 02LSW710 | SUMP TANK-802 LEVEL SWITCH PDS | FCK |  | 52 | 19 | E | 31 | 07.08.23 | 07.08.24
139 | HRD/DCW | 04LI1411 | POND WATER TANK LEVEL | FCK |  | 52 | 19 | E | 29 | 07.08.23 | 07.08.24
140 | GEHO | 11FS6-880 | PROPELLING LIQUID FLOW SWITCH | FCK |  | 52 | 19 |  | 37 | 08.08.23 | 08.08.24
141 | GEHO | 11FS6-881 | PROPELLING LIQUID FLOW SWITCH | FCK |  | 52 | 19 |  | 37 | 10.08.23 | 10.08.24
142 | PD AREA | 02FT503 | PH-2 PDS STEAM FLOW 6 ATA | CAL | 2 | 52 | 19 |  | 11 | 10.08.23 | 10.08.24
143 | PD AREA | 02LT503 | SLURRY HEATING TK 503 LEVEL | FCK |  | 52 | 19 | E | 29 | 12.08.23 | 12.08.24
144 | PD AREA | 02TT506 | SLURRY TK.503 TEMPERATURE | FCK |  | 52 | 19 |  | 44 | 12.08.23 | 12.08.24
145 | GEHO | 11PT6-880 | PROPELLING LIQUID PR. TXR | CAL |  | 52 | 20 |  | 8 | 14.08.23 | 14.08.24
146 | GEHO | 11PT6-881 | PROPELLING LIQUID PR. TXR | CAL |  | 52 | 20 |  | 8 | 14.08.23 | 14.08.24
147 | PD AREA | 02LT508 | PRE-DESILICATION TK 508 LEVEL | FCK |  | 52 | 20 | E | 29 | 16.08.23 | 16.08.24
148 | PD AREA | 02PT506 | PH-1 PDS TK. 503 STEAM INTERNAL PRESSURE | CAL | 1 | 52 | 20 |  | 11 | 18.08.23 | 18.08.24
149 | HRD/DCW | 04LI1416 | 2% SOLLUTION TANK LEVEL | FCK |  | 52 | 20 | E | 29 | 18.08.23 | 18.08.24
150 | PD AREA | 02FT707 | PDS TK-703 STEAM FLOW | CAL | 2 | 52 | 20 |  | 11 | 19.08.23 | 19.08.24
151 | PD AREA | 02FT709 | PDS TK-702 STEAM FLOW | CAL | 2 | 52 | 20 |  | 11 | 19.08.23 | 19.08.24
152 | PD AREA | 02LT702/ 703 | PDS HEATING TK-702/ 703 LEVEL | FCK |  | 52 | 21 | E | 29 | 22.08.23 | 22.08.24
153 | PD AREA | 02LT704 | PDS TANK 704 LEVEL | FCK |  | 52 | 21 | E | 29 | 22.08.23 | 22.08.24
154 | PD AREA | 02LT705 | PDS TANK 705 LEVEL | FCK |  | 52 | 21 | E | 29 | 24.08.23 | 24.08.24
155 | PD AREA | 02LT706 | PDS TANK 706 LEVEL | FCK |  | 52 | 21 | E | 29 | 24.08.23 | 24.08.24
156 | PD AREA | 02LT707 | PDS TANK 707 LEVEL | FCK |  | 52 | 21 | E | 29 | 25.08.23 | 25.08.24
157 | BALL MILL | 02PT855 | BM-701 GB OIL PRESSURE TXR | CAL | 1 | 52 | 21 |  | 11 | 25.08.23 | 25.08.24
158 | BALL MILL | 02FT 702 | BM701 FE SL FLOW | FCK |  | 52 | 21 |  | 55 | 26.08.23 | 26.08.24
159 | BALL MILL | 02WT701 | BM701 BAUXITE FLOW WBC-701 | CAL | 2 | 52 | 21 |  | 4 | 26.08.23 | 26.08.24
160 | HRD/DCW | 04LI1417 | 1% SOLLUTION TANK LEVEL | FCK |  | 52 | 22 | E | 29 | 28.08.23 | 28.08.24
161 | GEHO | 11PT7-880 | AIR PR. TXR | CAL | 1 | 52 | 22 |  | 8 | 28.08.23 | 28.08.24
162 | GEHO | 11PT7-881 | AIR PR. TXR | CAL | 1 | 52 | 22 |  | 8 | 30.08.23 | 30.08.24
163 | EFFLUENT | 36PHI04 | UP STREAM SABARI LAKE PH INDICATOR | CAL | 1 | 52 | 22 |  | 64 | 30.08.23 | 30.08.24
164 | EFFLUENT | 36PHI05 | DOWN STREAM SABARI LAKE PH INDICATOR | CAL | 1 | 52 | 22 |  | 64 | 31.08.23 | 31.08.24
165 | EFFLUENT | 36PHT04 | PH TRX(UP STREAM SABARI LAKE) | CAL | 1 | 52 | 22 | E | 20 | 31.08.23 | 31.08.24
166 | EFFLUENT | 36PHT05 | PH TRX(DOWN STREAM SABARI LAKE) | CAL | 1 | 52 | 22 | E | 20 | 01.09.23 | 01.09.24
167 | PD AREA | 02FCV703 | TANK 702 STEAM FLOW C/V | CAL | 5 | 52 | 23 |  | 12 | 04.09.23 | 04.09.24
168 | PD AREA | 02FCV704 | TANK 703 STEAM FLOW C/V | CAL | 5 | 52 | 23 |  | 12 | 04.09.23 | 04.09.24
169 | DIGESTION | 03TT701 | PH-III DIGESTION TANK 708 O/L TEMPERATURE | FCK |  | 52 | 23 |  | 44 | 06.09.23 | 06.09.24
170 | DIGESTION | 03TT702 | PH-III DIGESTION TANK 709 O/L TEMPERATURE | FCK |  | 52 | 23 |  | 44 | 06.09.23 | 06.09.24
171 | BALL MILL | 02FCV701 | BM701 MAIN SL FLOW C/V | CAL | 5 | 52 | 23 |  | 12 | 07.09.23 | 07.09.24
172 | BALL MILL | 02FCV702 | BM701 FE SL FLOW C/V | CAL | 5 | 52 | 23 |  | 12 | 09.09.23 | 09.09.24
173 | PD AREA | 02LT509 | PRE-DESILICATION TK 509 LEVEL | FCK |  | 52 | 23 | E | 29 | 09.09.23 | 09.09.24
174 | LIME | 56FT1165 | P 1165 A & B E/M FLOW TRANSMITER | FCK |  | 52 | 24 |  | 55 | 11.09.23 | 11.09.24
175 | LIME | 56FT1166 | P 1166 A & B E/M FLOW TRANSMITER | FCK |  | 52 | 24 |  | 55 | 11.09.23 | 11.09.24
176 | PD AREA | 02LT1005 | PD TANK 1005 LEVEL INDICATION | FCK |  | 52 | 24 | E | 29 | 13.09.23 | 13.09.24
177 | DESILICATION | 03PHT701 | GATE-1 PH TRANSMITTER | CAL | 2 | 52 | 24 |  | 20 | 13.09.23 | 13.09.24
178 | TTD | 04XT940 | TTD 908 RAKE TORQUE | FCK |  | 52 | 24 |  | 58 | 14.09.23 | 14.09.24
179 | TTD | 04XT950 | TTD 909 RAKE TORQUE | FCK |  | 52 | 24 |  | 58 | 14.09.23 | 14.09.24
180 | GEHO | 11PT-880 | SUCTION AIR VESSEL PR. TXR | CAL | 1 | 52 | 24 |  | 11 | 16.09.23 | 16.09.24
181 | BALL MILL | 02PI005 | GEAR BOX LUB OIL PR. TRX BM-005 | CAL | 1 | 52 | 24 |  | 11 | 16.09.23 | 16.09.24
182 | DIGESTION | 03LCV104 | PH-II DIGESTION RC POT-002 LEVEL | CAL | 5 | 52 | 25 |  | 12 | 18.09.23 | 18.09.24
183 | DIGESTION | 03TT703 | PH-III DIGESTION TANK 710 O/L TEMPERATURE | FCK |  | 52 | 25 |  | 44 | 18.09.23 | 18.09.24
184 | DIGESTION | 03TT704 | PH-III DIGESTION TANK 711 O/L TEMPERATURE | FCK |  | 52 | 25 |  | 44 | 19.09.23 | 19.09.24
185 | DESILICATION | 03LCV124 | PH-II DESILICATION RC POT LEVEL | CAL | 5 | 52 | 25 |  | 12 | 19.09.23 | 19.09.24
186 | DESILICATION | 03LSW42 | SUMP TANK LEVEL SWITCH DESILICATION | FCK |  | 52 | 25 | E | 31 | 22.09.23 | 22.09.24
187 | CRUSHER | 01FS701 | NEW CRUSHER OIL FLOW SWITCH | FCK |  | 52 | 25 |  | 37 | 22.09.23 | 22.09.24
188 | BALL MILL | 02LI1010 | SILO-1001 LEVEL | FCK |  | 52 | 25 |  | 29 | 23.09.23 | 23.09.24
189 | BALL MILL | 02LI1020 | SILO-1002 LEVEL | FCK |  | 52 | 26 |  | 29 | 25.09.23 | 25.09.24
190 | BALL MILL | 02FCV518 | FE SL FLOW C/V TO BM003 | CAL | 5 | 52 | 26 |  | 12 | 25.09.23 | 25.09.24
191 | PD AREA | 02FT501 | PH-1 PDS STEAM FLOW 6 ATA | CAL | 2 | 52 | 26 |  | 11 | 27.09.23 | 27.09.24
192 | PD AREA | 02PT504 | PH-1 PDS TK. 501 STEAM INTERNAL PRESSURE | CAL | 1 | 52 | 26 |  | 11 | 27.09.23 | 27.09.24
193 | BALL MILL | 02FCV1001 | MAIN SL FLOW C/V TO BM-1001 | CAL | 5 | 52 | 26 |  | 12 | 28.09.23 | 28.09.24
194 | BALL MILL | 02FCV1002 | FEED END SL FLOW C/V TO BM-1001 | CAL | 5 | 52 | 26 |  | 12 | 28.09.23 | 28.09.24
195 | BALL MILL | 02FI1001 | MAIN SL FLOW TO BM-1001 | FCK |  | 52 | 26 |  | 55 | 29.09.23 | 29.09.24
196 | BALL MILL | 02FI1002 | FEED END SL FLOW TO BM-1001 | FCK |  | 52 | 27 |  | 55 | 03.10.23 | 03.10.24
197 | BALL MILL | 02WI1001 | BAUXITE FLOW TO BM-1001 | CAL | 1 | 52 | 27 |  | 4 | 03.10.23 | 03.10.24
198 | BALL MILL | 02WI1002 | BAUXITE FLOW TO BM-1002 | CAL | 2 | 52 | 27 |  | 4 | 05.10.23 | 05.10.24
199 | BALL MILL | 02FCV517 | MAIN SL FLOW C/V TO BM004 | CAL | 5 | 52 | 27 |  | 12 | 05.10.23 | 05.10.24
200 | BALL MILL | 02FCV520 | FE SL FLOW C/V TO BM004 | CAL | 5 | 52 | 27 |  | 12 | 06.10.23 | 06.10.24
201 | BALL MILL | 02FT520 | FE SL FLOW TO BM004 | FCK |  | 52 | 27 |  | 55 | 06.10.23 | 06.10.24
202 | DIGESTION | 03FT706 | PH-III DIGESTION STEAM FLOW. | CAL | 2 | 52 | 27 |  | 11 | 06.10.23 | 06.10.24
203 | DIGESTION | 03LT701A/ B | PH-III DIGESTION TANK 712/ 713 LEVEL. | FCK |  | 52 | 27 | E | 29 | 07.10.23 | 07.10.24
204 | DIGESTION | 03TI1011 | DIG-IV 1ST TANK TEMP | FCK |  | 52 | 27 |  | 44 | 07.10.23 | 07.10.24
205 | DESILICATION | 03TI1019 | DES-IV 1ST TANK TEMP | FCK |  | 52 | 28 |  | 44 | 09.10.23 | 09.10.24
206 | GEHO | 11PT-881 | SUCTION AIR VESSEL PR. TXR | CAL | 1 | 52 | 28 |  | 11 | 09.10.23 | 09.10.24
207 | GEHO | 11PT-891 | GEHO PUMP DISCHARGE PR. TXR-1 | CAL |  | 52 | 28 |  | 11 | 10.10.23 | 10.10.24
208 | LIME | 56FT101 | SODIC COND MAIN FLO Trx. | FCK |  | 52 | 28 |  | 55 | 10.10.23 | 10.10.24
209 | BALL MILL | 02FCV1003 | MAIN SL FLOW C/V TO BM-1002 | CAL | 5 | 52 | 28 |  | 12 | 12.10.23 | 12.10.24
210 | BALL MILL | 02FCV1004 | FEED END SL FLOW C/V TO BM-1002 | CAL | 5 | 52 | 28 |  | 12 | 12.10.23 | 12.10.24
211 | BALL MILL | 02FI1003 | MAIN SL FLOW TO BM-1002 | FCK |  | 52 | 28 |  | 55 | 14.10.23 | 14.10.24
212 | BALL MILL | 02FI1004 | FEED END SL FLOW TO BM-1002 | FCK |  | 52 | 29 |  | 55 | 16.10.23 | 16.10.24
213 | BALL MILL | 02LI1002 | BM-1001 MST LEVEL | FCK |  | 52 | 29 | E | 29 | 16.10.23 | 16.10.24
214 | BALL MILL | 02LI1003 | BM-1002 MST LEVEL | FCK |  | 52 | 29 | E | 29 | 18.10.23 | 18.10.24
215 | BALL MILL | 02LSW1000 | BM-1001/1002 SUMP PUMP LEVEL SWITCH | FCK |  | 52 | 29 | E | 31 | 18.10.23 | 18.10.24
216 | DESILICATION | 03PCV130 | PH-II DESILICATION PRESSURE C/V | CAL | 5 | 52 | 29 |  | 12 | 20.10.23 | 20.10.24
217 | SETTLER | 04LT908 | SETTLER 901 LIQUOR LEVEL | FCK |  | 52 | 29 | E | 29 | 20.10.23 | 20.10.24
218 | SETTLER | 04XT901 | SETTLER 901 RAKE TORQUE | FCK |  | 52 | 29 |  | 57 | 21.10.23 | 21.10.24
219 | SETTLER | 04XT902 | SETTLER 902 RAKE TORQUE | FCK |  | 52 | 29 |  | 57 | 21.10.23 | 21.10.24
220 | BALL MILL | 02TI2200A | Feed End Trunion Bearing Temparature Of BM-1002 | FCK |  | 52 | 30 |  | 44 | 23.10.23 | 23.10.24
221 | BALL MILL | 02TI2200B | Feed End Trunion Bearing Temparature Of BM-1002 | FCK |  | 52 | 30 |  | 44 | 23.10.23 | 23.10.24
222 | BALL MILL | 02TI2200C | Feed End Trunion Bearing Temparature Of BM-1002 | FCK |  | 52 | 30 |  | 44 | 25.10.23 | 25.10.24
223 | BALL MILL | 02TI2200D | Discharge End Trunion Bearing Temparature Of BM-1002 | FCK |  | 52 | 30 |  | 44 | 25.10.23 | 25.10.24
224 | BALL MILL | 02TI2200E | Discharge End Trunion Bearing Temparature Of BM-1002 | FCK |  | 52 | 30 |  | 44 | 27.10.23 | 27.10.24
225 | BALL MILL | 02TI2200F | Discharge End Trunion Bearing Temparature Of BM-1002 | FCK |  | 52 | 30 |  | 44 | 27.10.23 | 27.10.24
226 | DIGESTION | 03LT101A/ B | PH-I DIGESTION TK-20/ 265 LEVEL | FCK |  | 52 | 30 | E | 29 | 28.10.23 | 28.10.24
227 | SETTLER | 04LT909 | SETTLER 904 LIQUOR LEVEL | FCK |  | 52 | 30 | E | 29 | 28.10.23 | 28.10.24
228 | SETTLER | 04LT911 | SETTLER 902 LIQUOR LEVEL | FCK |  | 52 | 31 | E | 29 | 30.10.23 | 30.10.24
229 | SETTLER | 04LT912 | SETTLER 905 LIQUOR LEVEL | FCK |  | 52 | 31 | E | 29 | 30.10.23 | 30.10.24
230 | RECLAIMER | 52WT101 | RECLAIMER WEIGHT TRANSMITTER | CAL | 2 | 52 | 31 |  | 4 | 01.11.23 | 01.11.24
231 | CRUSHER | 01TSW001 | CR-1 BTS | FCK |  | 52 | 31 |  | 67 | 01.11.23 | 01.11.24
232 | CRUSHER | 01TSW002 | CRUSHER-2 BTS | FCK |  | 52 | 31 |  | 67 | 02.11.23 | 02.11.24
233 | BALL MILL | 02TI2201A | FE Pinion Bearing temperature Of BM-1002 | FCK |  | 52 | 31 |  | 44 | 02.11.23 | 02.11.24
234 | BALL MILL | 02TI2201B | DE Pinion Bearing temperature Of BM-1002 | FCK |  | 52 | 31 |  | 44 | 02.11.23 | 02.11.24
235 | BALL MILL | 02LSW007 | SUMP TANK LEVEL SWITCH | FCK |  | 52 | 32 | E | 31 | 04.11.23 | 04.11.24
236 | BALL MILL | 02LSW008 | SUMP TANK LEVEL SWITCH | FCK |  | 52 | 32 | E | 31 | 04.11.23 | 04.11.24
237 | DESILICATION | 03LT121A/ B | DESILICATION TK.44/ 45 LEVEL TXR | FCK |  | 52 | 32 | E | 29 | 06.11.23 | 06.11.24
238 | SETTLER | 04XT906 | SETTLER 906 RAKE TORQUE | FCK |  | 52 | 32 |  | 57 | 06.11.23 | 06.11.24
239 | LIME | 56FCV101 | SODIC COND MAIN FLO C/VALVE | CAL | 5 | 52 | 32 |  | 12 | 08.11.23 | 08.11.24
240 | LIME | 56FCV102 | SODIC COND FLO C/V SPRAY | CAL | 5 | 52 | 32 |  | 12 | 08.11.23 | 08.11.24
241 | LIME | 56FT103 | SLAKER-4 SODIC COND F.T. | FCK |  | 52 | 32 |  | 55 | 09.11.23 | 09.11.24
242 | BALL MILL | 02TI2100A | Feed End Trunion Bearing Temparature Of BM-1001 | FCK |  | 52 | 32 |  | 44 | 09.11.23 | 09.11.24
243 | BALL MILL | 02TI2100B | Feed End Trunion Bearing Temparature Of BM-1001 | FCK |  | 52 | 33 |  | 44 | 11.11.23 | 11.11.24
244 | BALL MILL | 02TI2100C | Feed End Trunion Bearing Temparature Of BM-1001 | FCK |  | 52 | 33 |  | 44 | 11.11.23 | 11.11.24
245 | BALL MILL | 02TI2100D | Discharge End Trunion Bearing Temparature Of BM-1001 | FCK |  | 52 | 33 |  | 44 | 13.11.23 | 13.11.24
246 | BALL MILL | 02TI2100E | Discharge End Trunion Bearing Temparature Of BM-1001 | FCK |  | 52 | 33 |  | 44 | 13.11.23 | 13.11.24
247 | BALL MILL | 02TI2100F | Discharge End Trunion Bearing Temparature Of BM-1001 | FCK |  | 52 | 33 |  | 44 | 14.11.23 | 14.11.24
248 | BALL MILL | 02TI2203A | Main Motor Bearing Temperature-NDE Of BM-1002 | FCK |  | 52 | 33 |  | 44 | 14.11.23 | 14.11.24
249 | BALL MILL | 02TI2203B | Main Motor Bearing Temperature-DE Of BM-1002 | FCK |  | 52 | 33 |  | 44 | 16.11.23 | 16.11.24
250 | DIGESTION | 03PCV 701 | PH-III DIGESTION STEAM C/V TO TANK 708 | CAL | 5 | 52 | 34 |  | 12 | 20.11.23 | 20.11.24
251 | DIGESTION | 03PCV 702 | PH-III DIGESTION STEAM C/V TO TANK 709 | CAL | 5 | 52 | 34 |  | 12 | 20.11.23 | 20.11.24
252 | BALL MILL | 02TI2101A | FE Pinion Bearing temperature Of BM-1001 | FCK |  | 52 | 34 |  | 44 | 22.11.23 | 22.11.24
253 | BALL MILL | 02TI2101B | DE Pinion Bearing temperature Of BM-1001 | FCK |  | 52 | 34 |  | 44 | 22.11.23 | 22.11.24
254 | BALL MILL | 02LT109 | BAUXITE SILO LEVEL TRANSMITTER BM-004 | FCK |  | 52 | 34 |  | 29 | 24.11.23 | 24.11.24
255 | PD AREA | 02LT511 | PRE-DESILICATION TK 511 LEVEL | FCK |  | 52 | 34 | E | 29 | 24.11.23 | 24.11.24
256 | RECLAIMER | 52WI1003 | RECLAIMER 003 BELT WEIGHER | CAL | 2 | 52 | 34 |  | 4 | 25.11.23 | 25.11.24
257 | PD AREA | 02FT508 | PH-1 PRIMARY GL FLOW METER | FCK |  | 52 | 34 |  | 55 | 25.11.23 | 25.11.24
258 | PD AREA | 02FT508A | S/B HDR PRIMARY GL FLOW METER | FCK |  | 52 | 35 |  | 55 | 28.11.23 | 28.11.24
259 | PD AREA | 02FT509 | PH-2 PRIMARY GL FLOW METER | FCK |  | 52 | 35 |  | 55 | 28.11.23 | 28.11.24
260 | DESILICATION | 03PCV122 | PH-I DESILICATION PRESSURE C/V | CAL | 5 | 52 | 35 |  | 12 | 29.11.23 | 29.11.24
261 | SETTLER | 04LT910 | SETTLER 906 LIQUOR LEVEL | FCK |  | 52 | 35 | E | 29 | 29.11.23 | 29.11.24
262 | SETTLER | 04LT913 | SETTLER 907 LIQUOR LEVEL | FCK |  | 52 | 35 | E | 29 | 30.11.23 | 30.11.24
263 | SETTLER | 04XT903 | SETTLER 903 RAKE TORQUE | FCK |  | 52 | 35 |  | 57 | 30.11.23 | 30.11.24
264 | SETTLER | 04XT907 | SETTLER 907 RAKE TORQUE | FCK |  | 52 | 35 |  | 57 | 01.12.23 | 01.12.24
265 | BALL MILL | 02TI2103A | Main Motor Bearing Temperature-NDE Of BM-1001 | FCK |  | 52 | 35 |  | 44 | 01.12.23 | 01.12.24
266 | BALL MILL | 02TI2103B | Main Motor Bearing Temperature-DE Of BM-1001 | FCK |  | 52 | 35 |  | 44 | 02.12.23 | 02.12.24
267 | BALL MILL | 02FCV516 | MAIN SL FLOW C/V TO BM005 | CAL | 5 | 52 | 36 |  | 12 | 04.12.23 | 04.12.24
268 | BALL MILL | 02FCV519 | FE SL FLOW C/V TO BM005 | CAL | 5 | 52 | 36 |  | 12 | 04.12.23 | 04.12.24
269 | BALL MILL | 02FT519 | FE SL FLOW TO BM005 | FCK |  | 52 | 36 |  | 55 | 06.12.23 | 06.12.24
270 | PD AREA | 02LI1006 | PD TANK 1006 LEVEL | FCK |  | 52 | 36 | E | 29 | 06.12.23 | 06.12.24
271 | PD AREA | 02LI1007 | PD TANK 1007 LEVEL | FCK |  | 52 | 36 | E | 29 | 07.12.23 | 07.12.24
272 | PD AREA | 02LI1008 | PD TANK 1008 LEVEL | FCK |  | 52 | 36 | E | 29 | 07.12.23 | 07.12.24
273 | PD AREA | 02LSW1001 | PD-IV SUMP PUMP LEVEL SWITCH | FCK |  | 52 | 36 | E | 31 | 08.12.23 | 08.12.24
274 | PD AREA | 02PT1004 | PD PH-IV STEAM INTERNAL PRESSURE | CAL | 1 | 52 | 36 |  | 11 | 08.12.23 | 08.12.24
275 | SETTLER | 04LT914 | SETTLER 903 LIQUOR LEVEL | FCK |  | 52 | 37 | E | 29 | 11.12.23 | 11.12.24
276 | SETTLER | 04LT921 | 2% SOLUTION TANK 974 LEVEL | FCK |  | 52 | 37 | E | 29 | 11.12.23 | 11.12.24 | Updated
277 | SETTLER | 04LT924 | 2% SOLUTION TANK 975 LEVEL | FCK |  | 52 | 37 | E | 29 | 14.12.22 | 14.12.23
278 | PD AREA | 02TI1004A | PD HEATING TANK 1004A TEMPARATURE | FCK |  | 52 | 37 |  | 44 | 15.12.22 | 15.12.23
279 | PD AREA | 02TI1004B | PD HEATING TANK 1004B TEMPARATURE | FCK |  | 52 | 37 |  | 44 | 15.12.22 | 15.12.23
280 | PD AREA | 02FCV501 | STEAM FLOW CONTROL VALVE TK-501 | CAL | 5 | 52 | 37 |  | 12 | 17.12.22 | 17.12.23
281 | PD AREA | 02FCV502 | STEAM FLOW CONTROL VALVE TK-502 | CAL | 5 | 52 | 37 |  | 12 | 17.12.22 | 17.12.23
282 | PD AREA | 02FCV503 | STEAM FLOW CONTROL VALVE TK-503 | CAL | 5 | 52 | 38 |  | 12 | 19.12.22 | 19.12.23
283 | BALL MILL | 02LT103 | BAUXITE SILO-2 LEVEL TRANSMITTER | FCK |  | 52 | 38 |  | 29 | 19.12.22 | 19.12.23
284 | PD AREA | 02FT1009 | PD-IV STEAM FLOW DP TRANSMITTER | CAL | 1 | 52 | 38 |  | 11 | 21.12.22 | 21.12.23
285 | PD AREA | 02FCV1005 | PH-IV PRIMARY GL CONTROL VALVE | CAL | 5 | 52 | 38 |  | 12 | 22.12.22 | 22.12.23
286 | PD AREA | 02PCV1004 | PD -IV HEATING TANK TEMPARATURE CONTROL VALVE | CAL | 5 | 52 | 38 |  | 12 | 22.12.22 | 22.12.23
287 | DIGESTION | 03LCV102 | PH-I DIGESTION RC POT-001 LEVEL C/V | CAL | 5 | 52 | 38 |  | 12 | 24.12.22 | 24.12.23
288 | LIME | 56WT101 | CONV-67 WEIGHT TXR | CAL | 2 | 52 | 38 |  | 4 | 24.12.22 | 24.12.23
289 | DIGESTION | 03LI1026 | DIG PH-IV RC POT 1026 LEVEL | CAL | 1 | 52 | 39 |  | 14 | 26.12.22 | 26.12.23
290 | DIGESTION | 03LI1027 | DIG PH-IV RC POT 1027 LEVEL | CAL | 1 | 52 | 39 |  | 14 | 26.12.22 | 26.12.23
291 | DILLUTION | 03LT133 | POND WATER TK-37 LEVEL | CAL | 1 | 52 | 39 | E | 14 | 28.12.22 | 28.12.23
292 | RECLAIMER | 52LS1001 | SUCTION VALVE LIMIT SWITCH | FCK |  | 52 | 39 |  | 37 | 28.12.22 | 28.12.23
293 | RECLAIMER | 52FS1001 | FLOAT SWITCH OIL SUMP | FCK |  | 52 | 39 |  | 37 | 29.12.22 | 29.12.23
294 | STACKER | 52WI1004 | STACKER-02/OLD STACKER BELT WEIGHER | CAL | 2 | 52 | 39 |  | 4 | 29.12.22 | 29.12.23
295 | PD AREA | 02PT505 | PH-1/2 PDS TK. 502 STEAM INTERNAL PRESSURE | CAL | 1 | 52 | 39 |  | 11 | 31.12.22 | 31.12.23
296 | DIGESTION | 03LT103A/ B | PH-II DIGESTION TK-25/ 266 LEVEL | FCK |  | 52 | 39 | E | 29 | 31.12.22 | 31.12.23
297 | DESILICATION | 03FCV1020 | DES PH-IV STEAM FLOW CONTROL VALVE | CAL | 5 | 52 | 40 |  | 12 | 02.01.23 | 02.01.24
298 | DESILICATION | 03TI1021 | DES PH-IV TANK 1021 O/L TEMPERATURE | FCK |  | 52 | 40 |  | 44 | 02.01.23 | 02.01.24
299 | DESILICATION | 03TI1025 | DES PH-IV TANK 1020 O/L TEMPERATURE | FCK |  | 52 | 40 |  | 44 | 03.01.23 | 03.01.24
300 | RECLAIMER | 52FPS1001 | PR. LINE FILTER PR. SWITCH | FCK |  | 52 | 40 |  | 37 | 05.01.23 | 05.01.24
301 | RECLAIMER | 52SFPS1001 | SUCTION FILTER PR. SWITCH | FCK |  | 52 | 40 |  | 37 | 05.01.23 | 05.01.24
302 | DIGESTION | 03CT1027 | DIG PH-IV RC POT 1027 CONDUCTIVITY | FCK |  | 52 | 40 |  | 36 | 07.01.23 | 07.01.24
303 | DIGESTION | 03CT701 | PH-III DIGESTION RC POT-701 CONDUCTIVITY | FCK |  | 52 | 40 |  | 36 | 07.01.23 | 07.01.24
304 | DIGESTION | 03CT702 | PH-III DIGESTION RC POT-702 CONDUCTIVITY | FCK |  | 52 | 41 |  | 36 | 09.01.23 | 09.01.24
305 | DIGESTION | 03LT702 | PH-III DIGESTION POT 701 LEVEL. | CAL | 2 | 52 | 41 |  | 14 | 09.01.23 | 09.01.24
306 | DIGESTION | 03LT703 | PH-III DIGESTION POT 702 LEVEL. | CAL | 2 | 52 | 41 |  | 14 | 10.01.23 | 10.01.24
307 | DILLUTION | 03LT506 | DILUTION TK-35 LEVEL TXR | FCK |  | 52 | 41 | E | 29 | 11.01.23 | 11.01.24
308 | DESILICATION | 03FI1020 | DES PH-IV STEAM FLOW | CAL | 1 | 52 | 41 |  | 11 | 12.01.23 | 12.01.24
309 | DESILICATION | 03PT1020 | DES PH-IV INTERNAL PRESSURE | CAL | 1 | 52 | 41 |  | 11 | 12.01.23 | 12.01.24
310 | DESILICATION | 03PT1029 | PH-4 SAND SEPARATION HYDRO CYCLONE FEED PRSSURE | CAL | 1 | 52 | 41 |  | 11 | 13.01.23 | 13.01.24
311 | DESILICATION | 03LCV122 | PH-I DESILICATION RC POT LEVEL | CAL | 5 | 52 | 41 |  | 12 | 13.01.23 | 13.01.24
312 | LIME | 31FV1101 | LIME ON/OFF VALVE TO PH-4 CAUS.TION | FCK |  | 52 | 41 |  | 38 | 14.01.23 | 14.01.24
313 | LIME | 31FV1102 | LIME ON/OFF VALVE TO PH-4 CAUS.TION | FCK |  | 52 | 42 |  | 38 | 16.01.23 | 16.01.24
314 | RECLAIMER | 52SV001 | RECLAIMER BOOM LUFFING UP/DOWN SOLENOID VALVE | FCK |  | 52 | 42 |  | 38 | 16.01.23 | 16.01.24
315 | CRUSHER | 01TSW1001 | CRUSHER 1001 HYDRO COUPLER TEMP SWITCH | FCK |  | 52 | 42 |  | 67 | 18.01.23 | 18.01.24
316 | CRUSHER | 01TT701DE | CRUSHER-701 DE BEARING OIL TEMP TXR | FCK |  | 52 | 42 |  | 44 | 18.01.23 | 18.01.24
317 | CRUSHER | 01TT701NDE | CRUSHER-701 NDE BEARING OIL TEMP TXR | FCK |  | 52 | 42 |  | 44 | 19.01.23 | 19.01.24
318 | CRUSHER | 01GTX1001 | CRUSHER-1001 GEAR BOX OIL TEMP TXR | FCK |  | 52 | 42 |  | 44 | 19.01.23 | 19.01.24
319 | CRUSHER | 01ZSS1001 | CRUSHER-1001 SPEED SWITCH | FCK |  | 52 | 42 |  | 68 | 21.01.23 | 21.01.24
320 | BALL MILL | 02TT852 | BM701 FE BEARING TEMPERATURE | FCK |  | 52 | 42 |  | 44 | 21.01.23 | 21.01.24
321 | DILLUTION | 03LT713 | MUD DISPOSAL TANK 717B LEVEL | FCK |  | 52 | 43 | E | 29 | 23.01.23 | 23.01.24
322 | DESILICATION | 03TT708B | DESILICATION TANK 725 O/L TEMPERATURE | FCK |  | 52 | 43 |  | 44 | 23.01.23 | 23.01.24
323 | RECLAIMER | 52SV701 | RECLAIMER 701 BOOM LUFFING UP SOLENOID VALVE | FCK |  | 52 | 43 |  | 38 | 25.01.23 | 25.01.24
324 | RECLAIMER | 52SV702 | RECLAIMER 701 BOOM LUFFING DOWN SOLENOID VALVE | FCK |  | 52 | 43 |  | 38 | 25.01.23 | 25.01.24
325 | RECLAIMER | 52SV703 | RECLAIMER 701 PROPERTIONAL CONTROL VALVE | FCK |  | 52 | 43 |  | 38 | 27.01.23 | 27.01.24
326 | BALL MILL | 02PI003 | BM-003 GEAR BOX LUB OIL PR. TXR | CAL | 1 | 52 | 43 |  | 11 | 27.01.23 | 27.01.24
327 | DIGESTION | 03FCV1012 | DIG PH-IV 1'ST STATION STEAM FLOW CONTROL VALVE | CAL | 5 | 52 | 43 |  | 12 | 28.01.23 | 28.01.24
328 | DIGESTION | 03FCV1015 | DIG PH-IV 2'ND STATION STEAM FLOW CONTROL VALVE | CAL | 5 | 52 | 43 |  | 12 | 28.01.23 | 28.01.24
329 | DIGESTION | 03FT1012 | DIG PH-IV 1'ST STATION STEAM FLOW | CAL | 1 | 52 | 44 |  | 11 | 30.01.23 | 30.01.24
330 | DIGESTION | 03FT1015 | DIG PH-IV 2'ND STATION STEAM FLOW | CAL | 1 | 52 | 44 |  | 11 | 30.01.23 | 30.01.24
331 | DIGESTION | 03LT501 | CONDENSATE POT 501 LEVEL | CAL | 2 | 52 | 44 |  | 14 | 01.02.23 | 01.02.24
332 | DIGESTION | 03LT502 | CONDENSATE POT 502 LEVEL | CAL | 2 | 52 | 44 |  | 14 | 01.02.23 | 01.02.24
333 | RECLAIMER | 52SV1001 | RECLAIMER 1001 BOOM LUFFING UP SOLENOID VALVE | FCK |  | 52 | 44 |  | 38 | 02.02.23 | 02.02.24
334 | RECLAIMER | 52SV1002 | RECLAIMER 1001 BOOM LUFFING DOWN SOLENOID VALVE | FCK |  | 52 | 44 |  | 38 | 02.02.23 | 02.02.24
335 | RECLAIMER | 52SV1003 | RECLAIMER 1001 PROPERTIONAL CONTROL VALVE | FCK |  | 52 | 44 |  | 38 | 04.02.23 | 04.02.24
336 | STACKER | 52SV002 | STACKER 001 BOOM LUFFING UP/DOWN SOLENOID VALVE | FCK |  | 52 | 44 |  | 38 | 04.02.23 | 04.02.24
337 | DIGESTION | 03CT1026 | DIG PH-IV RC POT 1026 CONDUCTIVITY | FCK |  | 52 | 45 |  | 36 | 06.02.23 | 07.02.24
338 | DIGESTION | 03LSW1018 | DIG PH-IV SUMP PUMP LEVEL SWITCH | FCK |  | 52 | 45 | E | 31 | 07.02.23 | 07.02.24
339 | DIGESTION | 03TI1012 | DIG PH-IV TANK 1012 O/L TEMPERATURE | FCK |  | 52 | 45 |  | 44 | 09.02.23 | 09.02.24
340 | DIGESTION | 03TI1013 | DIG PH-IV TANK 1013 O/L TEMPERATURE | FCK |  | 52 | 45 |  | 44 | 09.02.23 | 09.02.24
341 | DIGESTION | 03TI1014 | DIG PH-IV TANK 1014 O/L TEMPERATURE | FCK |  | 52 | 45 |  | 44 | 10.02.23 | 10.02.24
342 | DIGESTION | 03TI1015 | DIG PH-IV TANK 1015 O/L TEMPERATURE | FCK |  | 52 | 45 |  | 44 | 10.02.23 | 10.02.24
343 | DIGESTION | 03TI1016 | DIG PH-IV TANK 1016 O/L TEMPERATURE | FCK |  | 52 | 45 |  | 44 | 11.02.23 | 11.02.24
344 | DIGESTION | 03TI1017 | DIG PH-IV PUMP DISCHARGE TEMPERATURE | FCK |  | 52 | 45 |  | 44 | 11.02.23 | 11.02.24
345 | LIME | 56DT101A | P-1166 DENSITY TXR | CAL | 2 | 52 | 46 |  | 13 | 13.02.23 | 13.02.24
346 | LIME | 56DT101B | P-1165 DENSITY TXR | CAL | 2 | 52 | 46 |  | 13 | 13.02.23 | 13.02.24
347 | DIGESTION | 03PCV110 | PRESSURE CONTROL VALVE TK-21/22 | CAL | 5 | 52 | 46 |  | 12 | 15.02.23 | 15.02.24
348 | DIGESTION | 03PCV503 | PRESSURE CONTROL VALVE TK-23/24 | CAL | 5 | 52 | 46 |  | 12 | 16.02.23 | 16.02.24
349 | DIGESTION | 03TT505 | PH-II DIGESTION TK-21 TEMPERATURE | FCK |  | 52 | 46 |  | 44 | 17.02.23 | 17.02.24
350 | DIGESTION | 03TT506 | PH-II DIGESTION TK-22 TEMPERATURE | FCK |  | 52 | 46 |  | 44 | 17.02.23 | 17.02.24
351 | DIGESTION | 03TT507 | PH-II DIGESTION TK-23 TEMPERATURE | FCK |  | 52 | 46 |  | 44 | 18.02.23 | 18.02.24
352 | DIGESTION | 03TT508 | PH-II DIGESTION TK-24 TEMPERATURE | FCK |  | 52 | 47 |  | 44 | 20.02.23 | 20.02.24
353 | DESILICATION | 03LI1022 /1023 | DES PH-IV TANK 1022 / 1023 LEVEL | FCK |  | 52 | 47 | E | 29 | 22.02.23 | 22.02.24
354 | DESILICATION | 03LI1028 | DES PH-IV RC POT 1028 LEVEL | FCK |  | 52 | 47 | E | 29 | 23.02.23 | 23.02.24
355 | HRD/DCW | 03FI1025 | HRD-1/2 FEED FLOW FROM DES-4 | FCK |  | 52 | 47 |  | 55 | 23.02.23 | 23.02.24
356 | RECLAIMER | 52WT701 | RECLAIMER WEIGHT TRANSMITTER | CAL | 2 | 52 | 47 |  | 4 | 24.02.23 | 24.02.24
357 | DIGESTION | 03LI1016/ 1017 | DIG PH-IV TANK 1016/ 1017 LEVEL | FCK |  | 52 | 47 | E | 29 | 25.02.23 | 25.02.24
358 | DIGESTION | 03FT102 | PH-II DIGESTION STEAM FLOW | CAL | 2 | 52 | 47 |  | 11 | 25.02.23 | 25.02.24
359 | DIGESTION | 03TT501 | PH-I DIGESTION TK-16 TEMPERATURE | FCK |  | 52 | 48 |  | 44 | 27.02.23 | 27.02.24
360 | DIGESTION | 03TT502 | PH-I DIGESTION TK-17 TEMPERATURE | FCK |  | 52 | 48 |  | 44 | 27.02.23 | 27.02.24
361 | DIGESTION | 03TT503 | PH-I DIGESTION TK-18 TEMPERATURE | FCK |  | 52 | 48 |  | 44 | 28.02.23 | 28.02.24
362 | DIGESTION | 03TT504 | PH-I DIGESTION TK-19 TEMPERATURE | FCK |  | 52 | 48 |  | 44 | 28.02.23 | 28.02.24
363 | DESILICATION | 03CT1028 | DES PH-IV RC POT 1028 CONDUCTIVITY | FCK |  | 52 | 48 |  | 36 | 01.03.23 | 01.03.24
364 | DESILICATION | 03LI1024 | DES PH-IV SAND DILLUTION TANK 1024 LEVEL | FCK |  | 52 | 48 | E | 29 | 02.03.23 | 02.03.24
365 | DESILICATION | 03LSW1025 | DES PH-IV SUMP PUMP LEVEL SWITCH | FCK |  | 52 | 48 | E | 31 | 04.03.23 | 04.03.24
366 | HRD/DCW | 03DI1010 | HRD-1/2 FEED FLOW DENSITY FROM DES-4 | CAL | 2 | 52 | 48 |  | 13 | 04.03.23 | 04.03.24
367 | BALL MILL | 02BW502 | BM004 BELT WEIGHER | CAL | 2 | 52 | 49 |  | 4 | 06.03.23 | 06.03.24
368 | DIGESTION | 03LSW704 | SUMP TANK-803 LEVEL SWITCH DIGESTION | FCK |  | 52 | 49 | E | 31 | 07.03.23 | 07.03.24
369 | DILLUTION | 03LSW714 | SUMP TANK-804 LEVEL SWITCH DILUTION | FCK |  | 52 | 49 | E | 31 | 07.03.23 | 07.03.24
370 | DESILICATION | 03LSW708 | SUMP TANK-806 LEVEL SWITCH DESILICATION | FCK |  | 52 | 49 | E | 31 | 10.03.23 | 10.03.24
371 | HRD/DCW | 04DI1401AB | HRD-1 U/F DENSITY OF PUMPS 1401A/B | CAL | 2 | 52 | 49 |  | 13 | 10.03.23 | 10.03.24
372 | HRD/DCW | 04LI1401C | HRD-1 SURFACE LIQUOR LEVEL | FCK |  | 52 | 49 | E | 29 | 11.03.23 | 11.03.24
373 | HRD/DCW | 04LSW1424 | HRD-1/2 SUMP PUMP LSW | FCK |  | 52 | 49 | E | 31 | 11.03.23 | 11.03.24
374 | HRD/DCW | 04XV1401D | HRD-1/2 FEED ON/OFF VALVE | FCK |  | 52 | 50 |  | 38 | 13.03.23 | 13.03.24
375 | PD AREA | 02FT502 | PH-1 PDS STEAM FLOW 6 ATA | CAL | 2 | 52 | 50 |  | 11 | 14.03.23 | 14.03.24
376 | PD AREA | 02LT504 | PRE-DESILICATION TK 504 LEVEL | FCK |  | 52 | 50 | E | 29 | 14.03.23 | 14.03.24
377 | HRD/DCW | 04DI1402A | HRD-1/2 O/F DENSITY | CAL | 2 | 52 | 50 |  | 13 | 16.03.23 | 16.03.24
378 | HRD/DCW | 04DI1402B | HRD-1/2 O/F DENSITY | CAL | 2 | 52 | 50 |  | 13 | 16.03.23 | 16.03.24
379 | HRD/DCW | 04FI1402A | HRD-1/2 O/F TO DIASTER | FCK |  | 52 | 50 |  | 55 | 18.03.23 | 18.03.24
380 | HRD/DCW | 04FI1402B | HRD-1/2 O/F TO DIASTER | FCK |  | 52 | 50 |  | 55 | 18.03.23 | 18.03.24
381 | HRD/DCW | 04WI1401 | HRD-1 RAKE TORQUE | FCK |  | 52 | 51 |  | 58 | 20.03.23 | 20.03.24
382 | STACKER | 52SV003 | STACKER 002 BOOM LUFFING UP/DOWN SOLENOID VALVE | FCK |  | 52 | 51 |  | 38 | 21.03.23 | 21.03.24
383 | BALL MILL | 02LT104 | BAUXITE SILO LEVEL TRANSMITTER BM-003 | FCK |  | 52 | 51 |  | 29 | 22.03.23 | 22.03.24
384 | PD AREA | 02LT501 | SLURRY HEATING TK 501 LEVEL | FCK |  | 52 | 51 | E | 29 | 23.03.23 | 23.03.24
385 | PD AREA | 02LT502 | SLURRY HEATING TK 502 LEVEL | FCK |  | 52 | 51 | E | 29 | 23.03.23 | 23.03.24
386 | PD AREA | 02TT504 | SLURRY TK.501 TEMPERATURE | FCK |  | 52 | 51 |  | 44 | 25.03.23 | 25.03.24
387 | PD AREA | 02TT505 | SLURRY TK.502 TEMPERATURE | FCK |  | 52 | 51 |  | 44 | 25.03.23 | 25.03.24
388 | DESILICATION | 03LT123A/ B | DESILICATION TK.49/ 50 LEVEL TXR | FCK |  | 52 | 52 | E | 29 | 27.03.23 | 27.03.24
389 | HRD/DCW | 04LI1402C | HRD-2 SURFACE LIQUOR LEVEL | FCK |  | 52 | 52 | E | 29 | 27.03.23 | 27.03.24
390 | HRD/DCW | 04WI1402 | HRD-2 RAKE TORQUE | FCK |  | 52 | 52 |  | 58 | 29.03.23 | 29.03.24
391 | EFFLUENT | 36LI1211B | EFFLUENT PLANT POND-2 LVL TRX | FCK |  | 52 | 52 | E | 29 | 29.03.23 | 29.03.24
392 | EFFLUENT | 36LI1211A | EFFLUENT PLANT POND-1 LVL TRX | FCK |  | 52 | 52 | E | 29 | 30.03.23 | 30.03.24
393 | EFFLUENT | 36LI101 | OLD ACID TANK LEVEL TXR | FCK |  | 52 | 52 | E | 53 | 30.03.23 | 30.03.24
394 | EFFLUENT | 36LI102 | NEW ACID TANK LEVEL TXR | FCK |  | 52 | 52 | E | 53 | 31.03.23 | 31.03.24
395 | BALL MILL | 02RLI003 | REJECT CHUTE LEVEL OF BM003 | FCK |  | 52 | 52 |  | 29
396 | BALL MILL | 02RLI004 | REJECT CHUTE LEVEL OF BM004 | FCK |  | 52 | 52 |  | 29
397 | BALL MILL | 02RLI005 | REJECT CHUTE LEVEL OF BM005 | FCK |  | 52 | 52 |  | 29
398 | BALL MILL | 02RLI701 | REJECT CHUTE LEVEL OF BM701 | FCK |  | 52 | 52 |  | 29
399 | BALL MILL | 02RLI1001 | REJECT CHUTE LEVEL OF BM1001 | FCK |  | 52 | 52 |  | 29
400 | BALL MILL | 02RLI1002 | REJECT CHUTE LEVEL OF BM1002 | FCK |  | 52 | 52 |  | 29
401 | HRD/DCW | 04FI1436 | FLOW OF FLUSHING PUMP | FCK |  | 52 | 52 |  | 55

## PMPS PER WEEK
WEEK N. | FCK | CAL
35 | 8 | 1
36 | 5 | 3
37 | 5 | 2
38 | 1 | 6
39 | 3 | 5
40 | 6 | 1
41 | 3 | 6
42 | 8 | 0