## Area Items
INDENT | DATE | DESCRIPTION | QTY | EST VALUE(Rs) | TYPE | INDENTOR | Received | FC No | SCREENING | Status | DATE2 | TR | PO NO | DATE3 | PO VALUE | VENDOR | DEL. DUE | GR NO | DATE4 | STATUS
3000012080 |  | belt monitoring
3000012219 |  | rp analyser
1000075265 |  | submersion pH meter | 7 |  |  | k maniraja
1000071631 |  | lime diversion valve | 2 items |  | LTE | Agupta |  |  |  | PO Placed
1000074559 | 2006-04-27 | RADAR LEVEL TRANSMITTER BM-70. | 1 Item | 1449390 | STD | kmaniraja |  |  |  | drawn
1000074305 | 2026-04-06 | VOITH MAKE BTS SWITCHING SYSTEM | 2 Items | 871794 | Prop | K Maniraj |  |  |  | PO Placed
1000074151 | 2026-03-18 | Newton Belt Weigh Controller | 1 Item | 252350 | Prop | A Gupta |  |  |  | c/s
1000074150 | 2026-03-18 | Belt Scale Indicator IPA | 1 Item | 465944 | Prop | K maniraja |  |  |  | C/s
3000011339 | 2025-07-21 | DCS Card for Sodic Project | 2 Item | 1448541 | Capex | KMANIRAJA |  |  |  | drawn
5000001214 | 2025-08-14 | Pich Type COntrol Valve for Lime | 1 | 840000 | Develop | A Gupta |  |  |  | dropped
1000073128 | 2025-12-13 | submersion pH meter | 1 | 463230 | LTE | A Gupta |  |  |  | drawn
1000072540 | 2025-11-04 | acid dosing pump | 02Item |  | STD | Agupta |  |  |  | PO Placed
1000071727 | 2025-07-11 | ACME Belt Weigher | 02Item | 219777 | Prop | K Maniraja |  |  |  | dropped
1000071542 | 2025-07-12 | Eceentric Disc Valve | 03 Item | 1163730 | OPEN | K Mani/MRB |  |  |  | Po Placed
1000071791 | 2025-07-16 | Mass FLow Meter | 2 item | 403664 | LTE | K Maniraja |  |  |  | PO Placed | OSDR
1000071797 | 2025-07-16 | R-01 Belt Weigher Panel | 01 item | ₹ 312435 | prop | A Gupta
1000071895 | 2025-07-24 | probe for settler | 01 item | ₹ 1270000 | prop | k maniraja |  |  |  | drawn
1000071336 | 2025-06-04 | MEDIA CONVERTER | 01 Item | ₹ 127638 | OPEN | K MANIRAJA |  |  |  | c/s
1000071335 | 2025-06-04 | Interface Relays | 1 Item | ₹ 136200 | LTE | KMANIRAJA |  |  |  | c/s
1000070891 | 2025-04-25 | 3D Level transmitter | 1 Item | ₹ 499288 | Prop | A Gupta |  |  |  | c/s |  |  | 4500084417
1000071398 | 2025-06-11 | PORTABLE CONDUCTIVITY/pH METER 2 SIEMN | 2 Items | ₹ 429068 | Open | K Maniraja |  |  |  | Drawn Item 2
1000070797 | 2025-04-18 | Chute Block Switch | 1 Item | ₹ 28630 | Prop | A Gupta |  |  |  | c/s | to be chcecked
1000070824 | 2025-04-21 | Mud Probe | 1 Item | ₹ 2240000 | Prop | A Gupta |  |  |  | drawn |  |  | 4500085060
1000070147 | 2025-02-07 | Spare For VideoWall | 7 Item | ₹ 614660 | Prop | K Maniraja |  |  |  | drawn |  |  | 4500084432
1000070088 | 2025-02-03 | OIL FLOW SwITCH | 2 Item | ₹ 213436 | Open | K Maniraja |  |  |  | drawn
7000004718 | 2024-08-07 | Density & Level Evaluation Unit | 3 item | ₹7649566 | PROP | A Gupta |  |  |  | drawn |  |  | 4600003601
3000010785 | 2024-11-26 | PH IV Digestion steam CV | 1 item | ₹ 982,929 | LTE | A Gupta | ZCAP |  |  | C/S |  |  | 4500082250 | 2025-04-25 | [5 empty] | BUDGET CODE:12RM12CM002, ASSET CODE:9006941
3000010827 | 2024-12-14 | 3 inch lime CV | 1 item | ₹ 1,355,831 | LTE | A Gupta | ZCAP | [12 empty] | BUDGET CODE:12RM12CM002, ASSET CODE:9000581
3000010907 | 2025-01-07 | Eccentric disc Valve | 2 items | ₹ 1,679,005 | LTE | A Gupta/MR Behera | ZCAP |  |  | Dropped | [9 empty] | BUDGET CODE:12RM12CM002, ASSET CODE:90009614, 9009615
1000069865 | 2025-01-09 | Electronic speed switch & sensor probe | 2 items | ₹ 55,650 | STD | K Maniraja |  |  |  | drawn |  |  | 4500084753
1000069842 | 2025-01-07 | Sump pump level control switch | 1 item | ₹ 609,510 | LTE | A Gupta |  |  |  | drawn |  |  | 4500082503 | 2025-05-13
1000068909 | 2024-09-25 | Steam condensate Ball Valve | 2 items | ₹ 247,804 | OPEN | A Gupta |  | 671 | 2025-12-24 | drawn |  |  | 4500082431/34 | 2025-05-08
1000068876 | 2024-09-23 | Mass flowmeter for FDS | 1 item | ₹ 365,000 | LTE | A Gupta |  | 689 | 2025-12-24 | Cancelled
1000068720 | 2024-09-05 | Digital panel Indicator | 1 item | ₹ 123,655 | OPEN | A Gupta |  | 616 | 2025-10-24 | drawn |  |  | 4500082435 | 2025-05-08
1000068030 | 2024-06-25 | 3 way valve | 1 item | ₹ 89,134 | PROP | K Maniraja |  | 487 | 2025-07-24 | c/s |  |  | 4500081460 | 2025-02-25
1000067925 | 2024-06-15 | Torque transmitters for Settler | 1 item | ₹ 512,940 | STD | K Maniraja |  | 428 | 2024-06-19 | drawn |  |  | 4500083927 | 2024-11-30 | ₹ 522,500 | 115152 SANDURAX SOLUTIONS | 2025-04-26
1000066804 | 2024-05-23 | IPA Belt weigher spares & Load cell | 3 items | ₹ 1,084,346 | PROP | A Gupta/PA Bagde |  | 381 | 2024-06-05 | cancelled |  |  | 4500080114 | 2024-10-24 | ₹ 1,088,729 | 115152 SANDURAX SOLUTIONS | 2025-01-17 | 5000777079 | 2024-11-22
1000067592 | 2024-05-10 | PMW Positioner for Dezuric Valve | 1 item | ₹ 226,350 | PROP | A Gupta |  | 355 | 2024-05-22 | drawn |  |  | 4500081123 | 2025-01-28
1000067287 | 2024-04-11 | Newton Belt Weigh Controller | 1 item | ₹ 253,628 | PROP | A Gupta |  | 309 | 2024-05-08 | drawn |  |  | 4500079992 | 2024-10-12 | ₹ 245,000 | 119109 NEWTON WEIGHING SYSTEM PVT. LTD. | 2025-02-05 | 5000776110 | 2024-11-18
3000010215 | 2024-03-19 | DCS Server Spares | 2 items | ₹ 5,938,560 | PROP | K Maniraja | ZCAP | 4140 | FC Done | Dropped | [9 empty] | BUDGET CODE:12RM12CM002, ASSET CODE:9001108,9003922
1000067039 | 2024-03-18 | Mobrey Ultrasonic Probe | 1 item | ₹ 2,076,430 | PROP | A Gupta |  | 251 | 2024-04-10 | drawn |  |  | 4500080526 | 2024-11-29 | ₹ 11,200,000 | 108575 RAMAN INSTRUMENTS PVT. LTD. | 2025-03-07
1000066844 | 2024-03-02 | M2M ROUTER-Modem | 1 item | ₹ 54,876 | PROP | K Maniraja |  |  |  | cancelled
1000066845 | 2024-03-02 | Reclaimer_Stacker Anemometer | 1 item | ₹ 1,141,200 | OPEN | K Maniraja |  | 233 | 2024-04-03 | Partially delivered |  |  | 4500080363 (4 no's) | 2024-11-12 | ₹ 274,576 | 122686 ART LINE PRINTERS | 2025-02-14
1000066826 | 2024-03-01 | Acid Dosing Pumps | 2 items | ₹ 428,070 | STD | A Gupta |  | 173 | 2024-03-13 |  |  |  | 4500079864 | 2024-09-27 | ₹ 448,404 | 104550 INDUSTRIAL SOLUTIONS | 2025-01-05
1000066787 | 2024-02-27 | EM Flowmeter | 1 item | ₹ 498,000 | PROP | A Gupta |  | 252 | 2024-04-10 |  |  |  | 4500080238 | 2024-11-01 | ₹ 494,000 | 105320 KROHNE MARSHALL PVT. LTD. | 2025-02-18
1000066523 | 2024-02-06 | Distributor Block Switch | 2 items | ₹ 79,352 | PROP | A Gupta |  | 115 | 2024-02-28 |  |  |  | 4500079748 | 2024-09-19 | ₹ 76,177 | 120107 U3S ENGITECH PRIVATE LIMITED | 2025-01-17 | 5000774629 | 2024-11-09
1000066529 | 2024-02-06 | Keltron Actuator & Spares | 4 items | ₹ 1,174,201 | PROP | K Maniraja/PA Bagde |  | 249 | 2024-04-10 | drawn |  |  | 4500080778 | 2024-12-24 | ₹ 881,115 | 105352 KERALA STATE ELECTRONICS DEV. CORPN | 2025-04-20
1000066026 | 2023-12-21 | IL Pneumatic Positioner | 1 item | ₹ 120,000 | PROP | A Gupta |  | 683 | 2024-01-03 |  |  |  | 4500078589 | 2024-05-31 | ₹ 126,000 | 104498 INSTRUMENTATION LIMITED., | 2024-09-28 | 5000759479 | 2024-08-21
1000066029 | 2023-12-21 | Masonolian Spares for Control Valve | 5 items | ₹ 602,650 | PROP | A Gupta |  | 684 | 2024-01-03 |  |  |  | 4500079428 | 2024-08-16 | ₹ 667,188 | 106241 MANJIL ENTERPRISES, | 2024-12-08 | 5000783076 | 2024-12-23
1000064998 | 2023-09-11 | GEHO 1804 Spares | 8 items | ₹ 2,416,037 | PROP | A Gupta |  | 571 | 2023-09-23 | Part Item at C/S |  |  | 4500076893 | 2024-01-13 | ₹ 2,549,560 | 106083 Maruthi Engineering India LLP | 2024-07-11 | 5000774023 | 2024-11-06
1000064762 | 2023-08-22 | Power supply module | 1 item | ₹ 155,850 | STD | K Maniraja |  | 669 | 2023-11-28 | drawn |  |  | 4500078597 | 2024-06-01 | ₹ 179,068 | 107021 NAVEEN UDYOG, | 2024-09-29 | 5000759014 | 2024-08-17
1000064389 | 2023-07-24 | SIM Based wireless communication system | 1 item | ₹ 433,047 | OPEN | K Maniraja |  | 462 | 2023-08-16 | drawn |  |  | 4500079318 | 2024-08-08 | ₹ 431,000 | 123127 WIMATE TECHNOLOGY SOLUTIONS PRIVATE | 2024-10-23 | 5000769086 | 2024-10-09
1000064399 | 2023-07-24 | Vega Radar level transmitter | 1 item | ₹ 1,297,550 | STD | A Gupta |  | 446 | 2023-08-02 | drawn |  |  | 4500077206 | 2024-02-12 | ₹ 1,366,186 | 104111 HYDROMECH ENGINEERS | 2024-06-09 | 5000732344 | 2024-03-23
1000064382 | 2023-07-22 | Iot based flow measurement system at Water In take point | 1 item | ₹ 660,000 | PROP | A Gupta |  | FC Done | 2023-08-23 | drawn |  |  | 4500077056 | 2024-01-29 | ₹ 485,000 | 103234 FORBES MARSHALL PVT.LTD. | 2024-05-28 | 5000728127 | 2024-03-02
1000064037 | 2023-06-30 | BTS Switching element & complete set | 2 items | ₹ 709,162 | PROP | A Gupta |  | 405 | 2023-07-20 | drawn |  |  | 4500077538 | 2024-03-12 | ₹ 821,750 | 111427 VOITH TURBO PVT.LTD., | 2024-07-09 | 5000748667 | 2024-06-21
1000064011 | 2023-06-27 | Lotus spares | 4 items | ₹ 405,702 | PROP | A Gupta |  | 401 | 2023-07-20 | drawn |  |  | 4500077939 | 2024-04-05 | ₹ 378,394 | 105885 LOTUS WIRELESS TECHNOLOGIES(I)PVT.L | 2024-07-25 | 5000767023 | 2024-09-28
7000004529 | 2023-06-19 | HRD DCW Torque transmitters | 2 no's | ₹ 339,088 | PROP | K Maniraja |  | 383 | 2023-07-08 | drawn |  |  | 4600003383 | 2023-11-01
1000063866 | 2023-06-14 | Rail clamp SOV | 1 no | ₹ 71,932 | PROP | A Gupta |  | 362 | 2023-06-30 |  |  |  | 4500077552 | 2024-03-13 | ₹ 66,346 | 119767 GLOBAL HYDRAULICS | 2024-09-09 | 5000781767 | 2024-12-17
1000063823 | 2023-06-10 | New Stacker Spares | 3 no's | ₹ 67,976 | PROP | A Gupta |  | 329 | 2023-06-14 |  |  |  | 4500075614 | 2023-09-22 | ₹ 66,359 | 108588 RAJESH & COMPANY | 2024-03-20 | 5000765359 | 2024-09-21
1000063725 | 2023-06-02 | Bucket wheel reclaimer spares | 9 no's | ₹ 870,690 | PROP | A Gupta |  | 403 | 2023-07-20 |  |  |  | 4500077116 | 2024-02-02 | ₹ 800,747 | 107351 OSWAL HYDRAULICS & PNEUMATICS | 2024-06-01 | 5000745256 | 2024-05-31
1000063520 | 2023-05-18 | Chute block switch | 1 no | ₹ 28,116 | PROP | A Gupta |  | 304 | 2023-06-07 |  |  |  | 4500076421 | 2023-12-02 | ₹ 27,797 | 103128 EIP ENVIRO LEVEL CONTROLS PVT LTD | 2024-05-29 | 5000760362 | 2024-08-26
1000063268 | 2023-04-26 | Reclaimer boom PT | 1 no | ₹ 55,440 | PROP | K Maniraja |  | 534 | 2023-05-11 |  |  |  | 4500074562 | 2023-07-01 | ₹ 41,780 | 106121 MSA INSTRUMENTS, | 2023-12-25 | 5000726781 | 2024-02-24
1000063218 | 2023-04-20 | EIP 3D Level transmitter card | 1 no | ₹ 969,490 | PROP | A Gupta/M Gupta |  | 535 | 2023-05-18 |  |  |  | 4500075141 | 2023-08-10 | ₹ 484,745 | 103107 EIP ENVIRO LEVEL CONTROLS ( P ) LTD | 2024-02-03 | 5000705032 | 2023-11-06
1000063175 | 2023-04-15 | 16 inch Flowmeter | 1 no | ₹ 389,661 | STD | A Gupta |  | 533 | 2023-05-11 |  |  |  | 4500075948 | 2023-10-23 | ₹ 425,600 | 105407 KROHNE MARSHALL (P)LTD; | 2024-04-10 | 5000720748 | 2024-01-24
1000063128 | 2023-04-10 | Mass Flowmeter for FDS | 1 no | ₹ 244,844 | OPEN | A Gupta |  | 215 | 2023-04-26 |  |  |  | 4500078787 | 2024-06-26 | ₹ 365,000 | 109268 SIDHARATH ENTERPRISES, | 2024-10-23 | 5000752562 | 2024-07-12
1000062861 | 2023-03-15 | Smoke dust density analyser | 7 no | ₹ 481,982 | PROP | M Gupta |  | 159 | 2023-03-30 |  |  |  | 4500074096 | 2023-05-27 | ₹ 436,504 | 103234 FORBES MARSHALL PVT.LTD. | 2023-11-16 | 5000724294 | 2024-02-13
1000062735 | 2023-03-15 | Portable meter for RC Conductivity | 2 no's | ₹ 620,320 | OPEN/GeM | A Gupta |  | 330 | 2023-06-14 |  |  |  | 4500076379 | 2023-11-28 | ₹ 240,981 | 100047 AMALGAMATED BIOTECH | 2024-05-26 | 5000688404 | 2023-08-11
1000062746 | 2023-03-04 | Control valves | 6 no's | ₹ 517,990 | OPEN/GeM | A Gupta |  | 170 | 2023-04-11 |  |  |  | 4500075572 | 2023-09-15 | ₹ 540,937 | 122382 INSTRUMENTS AND SYSTEMS | 2024-02-26 | 5000720866 | 2024-01-25
3000009196 | 2023-03-03 | Beck Actuator | 1 no | ₹ 1,255,202 | PROP | K Maniraja | ZCAP | 3620 | 2023-04-11 |  |  |  | 4500075861 | 2023-10-13 | ₹ 1,255,201 | 120562 TECQNIKO ENGINEERS | 2024-04-10 | 5000747402 | 2024-06-14 | BUDGET CODE:12RM12CM002, ASSET CODE:9007010
1000062624 | 2023-02-20 | Sump pump level control switch | 1 no | ₹ 414,232 | OPEN/GeM | A Gupta |  | 93 | 2023-02-22 |  |  |  | PO DELETED |  |  |  |  | 5000722986 | 2024-02-06
1000062625 | 2023-02-20 | Acid dosing pump | 2 no's | ₹ 428,070 | STD | A Gupta |  | 91 | 2023-02-22 |  |  |  | 4500073236 | 2023-03-24 | ₹ 428,070 | 104550 INDUSTRIAL SOLUTIONS | 2023-09-20
3000009154 | 2023-02-18 | PH IV Digestion steam CV | 1 no | ₹ 893,145 | PROP | A Gupta | ZCAP | 3546 | 2023-02-22 |  |  |  | 4500073514 | 2023-04-11 | ₹ 954,299 | 121574 SEVERN GLOCON VALVES PVT LTD | 2023-10-07 | 5000721932 | 2024-01-31 | BUDGET CODE:12RM12CM002, ASSET CODE:9006941
1000062544 | 2023-02-13 | Control Valves | 3 no's | ₹ 699,973 | LTE | M Gupta |  | 158 | 2023-03-30 |  |  |  | 4500074215 | 2023-06-02 | ₹ 321,187 | 122382 INSTRUMENTS AND SYSTEMS | 2023-11-26
1000062509 | 2023-02-10 | Bucket wheel reclaimer spares | 21 no's | ₹ 1,737,610 | PROP | A Gupta |  | 89 | 2023-02-22 | [8 empty] | 5000724057 | 2024-02-12
1000062466 | 2023-02-07 | Settler load cell and transmitter | 1 no | ₹ 550,000 | OPEN/GeM | A Gupta |  | 79 | 2023-02-17 |  |  |  | 4500074323 | 2023-06-10 | ₹ 498,000 | 115152 SANDURAX SOLUTIONS | 2023-12-07 | 5000696406 | 2023-09-22
1000062365 | 2023-01-31 | Mobrey Ultrasonic probe | 1 item | ₹ 1,919,950 | PROP | A Gupta |  | 90 | 2023-02-22 |  |  |  | 4500073699 | 2023-04-27 | ₹ 2,015,950 | 108575 RAMAN INSTRUMENTS PVT. LTD. | 2023-10-24 | 5000685619 | 2023-07-29
3000009093 | 2023-01-28 | 16 inch 90 degree angle valve | 1 no | ₹ 2,453,068 | LTE | A Gupta | ZCAP | FC Done | 2023-02-11 |  |  |  | 4500074380 | 2023-06-17 | ₹ 1,903,925 | 120454 ENOCH CONTROLS PVT LTD | 2023-12-14 | 5000728727 | 2024-03-06 | BUDGET CODE:12RM12CM002, ASSET CODE:9006869
1000062158 | 2023-01-27 | Reclaimer 001 belt weighing system spares | 2 items | ₹ 348,480 | PROP | A Gupta |  | 56 | 2023-02-02 |  |  |  | 4500073067 | 2023-03-11 | ₹ 331,500 | 103295 FLSMIDTH PRIVATE LTD | 2023-09-07 | 5000691554 | 2023-08-28
1000062323 | 2023-01-25 | Pneumatic valve positioner | 1 item | ₹ 102,500 | PROP | M Gupta |  | 73 | 2023-02-11 |  |  |  | 4500073163 | 2023-03-20 | ₹ 120,000 | 104498 INSTRUMENTATION LIMITED., | 2023-09-14 | 5000766469 | 2024-09-26
3000009086 | 2023-01-20 | 2" Lime Control Valve | 1 no | ₹ 727,232 | LTE | A Gupta | ZCAP | 3524 | 2023-02-02 |  |  |  | 4500073512 | 2023-04-11 | ₹ 625,645 | 109365 SYNOTECH, | 2023-10-07 | 5000703268 | 2023-10-27 | BUDGET CODE:12RM12CM002, ASSET CODE:9001204
1000062220 | 2023-01-17 | Keltron Loader Spares | 7 items | ₹ 1,733,096 | PROP | M Gupta |  | 360 | 2023-06-30 |  |  |  | 4500075985 (1 item) | 2023-10-26 | ₹ 462,881 | 105408 KELTRON CONTROLS | 2024-02-24 | 5000695045 | 2023-09-14
3000009059 | 2023-01-05 | EIP Density Transmitter | 1 item | ₹ 6,992,832 | STD | M Gupta | ZCAP | [5 empty] | 4500072916 | 2023-02-27 | ₹ 6,876,000 | 103128 EIP ENVIRO LEVEL CONTROLS PVT LTD | 2023-08-24 | 5000677261 | 2023-06-17
1000061876 | 2022-12-13 | Steam Control valve | 3 items | ₹ 1,581,241 | OPEN/GeM | A Gupta |  | 171 | 2023-04-11 |  |  |  | 4500074361 (2 items) | 2023-06-15 | ₹ 563,221 | 106167 KSB MIL CONTROLS LIMITED | 2023-12-12 | 5000712721 | 2023-12-15
1000060611 | 2022-08-19 | IPA Make load cell | 1 no | ₹ 432,000 | PROP | M Gupta |  | 402 | 2022-09-21 |  |  |  | 4500071978 | 2022-12-10 | ₹ 444,600 | 115152 SANDURAX SOLUTIONS | 2023-06-08 | 5000641762 | 2023-01-03
1000060537 | 2022-08-11 | Yokogawa make PH Sensor | 1 no | ₹ 118,318 | PROP | M Gupta |  | 398 | 2022-09-21 |  |  |  | 4500072167 | 2022-12-18 | ₹ 117,620 | 111836 YOKOGAWA INDIA LIMITED | 2023-06-25 | 5000650721 | 2023-02-15
1000060391 | 2022-07-29 | Spares for Belt weigher system | 5 no's | ₹ 442,260 | PROP | M Gupta |  | 397 | 2022-09-21 |  |  |  | 4500071909 | 2022-12-03 | ₹ 420,147 | 119109 NEWTON WEIGHING SYSTEM PVT. LTD. | 2023-06-01 | 5000638118 | 2022-12-15
1000060202 | 2022-07-15 | Ellita CT & CR | 1 no | ₹ 125,400 | PROP | A Gupta |  | 401 | 2022-09-21 |  |  |  | 4500072141 | 2022-12-26 | ₹ 143,216 | 117969 Eletta Instrumentation India Pvt. | 2023-06-24 | 5000681049 | 2023-07-07
1000059995 | 2022-06-29 | 2" Lime Diversion valve | 1 no | ₹ 758,000 | OPEN/GeM | A Gupta |  | 259 | 2022-07-06 |  |  |  | 4500070528 | 2022-08-22 | ₹ 469,810 | 121551 CSD PROCESS CONTROL & AUTOMATION PV | 2022-12-31 | 5000648914 | 2023-02-07
1000059924 | 2022-06-23 | BTS Switching Element | 2 no's | ₹ 526,790 | PROP | M Gupta |  | 258 | 2022-07-06 |  |  |  | 4500071164 | 2022-10-04 | ₹ 709,163 | 111427 VOITH TURBO PVT.LTD., | 2023-04-01 | 5000642857 | 2023-01-07
1000059871 | 2022-06-17 | Repeater | 2 no's | ₹ 544,420 | STD | K Maniraja |  | 285 | 2022-07-21 |  |  |  | 4500071246 | 2022-10-11 | ₹ 668,644 | 113107 USHA AGENCIES | 2023-04-06 | 5000631173 | 2022-11-15
1000059729 | 2022-06-06 | Vega Radar Level Transmitter | 1 no | ₹ 615,755 | STD | M Gupta |  | 228 | 2022-06-22 |  |  |  | 4500070746 | 2022-09-05 | ₹ 653,114 | 104111 HYDROMECH ENGINEERS | 2023-03-04 | 5000620187 | 2022-09-22
1000059433 | 2022-05-17 | EIP 3D Level Transmitter Card | 1 no | ₹ 970,000 | PROP | M Gupta |  | 213 | 2022-06-08 |  |  |  | 4500070002 | 2022-07-15 | ₹ 969,492 | 103128 EIP ENVIRO LEVEL CONTROLS PVT LTD | 2023-01-11 | 5000631411 | 2022-11-16
3000008584 | 2022-05-07 | Hart Configurator | 1 no | ₹ 1,608,620 | STD | A Gupta | ZCAP | [5 empty] | 4500071368 | 2022-10-20 | ₹ 1,100,207 | 110247 SIBASHAKTI ELASTOMER | 2023-04-17 | 5000654339 | 2023-03-03

## Common Items
INDENT | DATE | DESCRIPTION | QTY | EST VALUE(Rs) | TYPE | INDENTOR | Received | FC No | SCREENING | Status | DATE2 | TR | PO NO | DATE3 | PO VALUE | VENDOR | DEL. DUE | GR NO | DATE4 | STATUS
1000067218 | 2024-04-06 | Ultrasonic Level Transmitter | 3 items | ₹ 547,743 | OPEN | Planning Cell |  | 286 | 2024-04-17 |  |  |  | 4500081134/33 | 2025-01-28
1000067666 | 2024-05-18 | 8 inch EM Flowmeter | 1 item | ₹ 2,512,400 | LTE | Planning Cell |  | 354 | 2024-05-22 |  |  |  | 4500081397 | 2025-02-20
1000068334 | 2024-07-29 | pH & Conductivity analyzer | 4 items | ₹ 899,024 | LTE | Planning Cell |  | 536 | 2025-08-24 | RFQ | 2024-08-03
1000068570 | 2024-08-22 | Multimeter | 1 item | ₹ 293,175 | OPEN | Planning Cell |  | 612 | 2025-10-24 | RFQ | 2024-08-30
1000067919 | 2024-06-24 | Pressure Gauge | 45 items | ₹ 930,826 | LTE | Planning Cell |  | 684 | 2025-12-24 | RFQ | 2024-08-26
1000063145 | 2023-04-12 | Radar level Transmitter | 2 no's | ₹ 2,456,047 | LTE | Planning |  | 258 | 2023-05-08 |  |  |  | 4500080323 (1 item) | 2024-11-08 | ₹ 258,361 | 106121 MSA INSTRUMENTS, | 2025-02-13
1000063241 | 2023-04-22 | EM Flowmeter-01 | 10 no's | ₹ 7,142,728 | LTE | Planning |  | 299 | 2023-06-02 |  |  |  | 4500078455 | 2024-05-17 | ₹ 8,048,400 | 105320 KROHNE MARSHALL PVT. LTD. | 2024-11-11 | 5000776574 | 2024-11-20
1000063296 | 2023-04-27 | Gland Packing | 8 no's | ₹ 61,862 | OPEN | Planning |  | 270 | 2023-05-18 |  |  |  | 4500075648 | 2023-09-26 | ₹ 60,618 | 107220 NEW ERA INDUSTRIES | 2024-03-24 | 5000708268 | 2023-11-23
1000063658 | 2023-05-29 | EM Flowmeter-02 | 7 no's | ₹ 1,598,271 | LTE | Planning |  | 300 | 2023-06-02 |  |  |  | 4500076409 (2 no's) | 2023-11-30 | ₹ 297,325 | 109268 SIDHARATH ENTERPRISES, | 2024-05-26 | 5000726104 | 2024-02-21
1000064240 | 2023-07-14 | AFR & IP | 8 items | ₹ 843,098 | OPEN | Planning |  | 425 | 2023-07-29 |  |  |  | 4500078197 (6 items) | 2024-04-25 | ₹ 461,422 | 123035 JAY SALES & SERVICES | 2024-08-10 | 5000748588 | 2024-06-21
1000064240 | 2023-07-14 | AFR & IP |  |  | OPEN | Planning | [6 empty] | 4500077839 (1 item) | 2024-03-30 | ₹ 818,352 | 121488 PROACTIVE TECHNOLOGIES | 2024-09-25 | 5000738338 | 2024-04-20
[13 empty] | 4500081298 | 2025-02-11
1000063865 | 2024-02-10 | Studs | 26 items | ₹ 402,950 | OPEN | Planning |  | 725 | 2024-02-21 |  |  |  | 4500079797 (11 items) | 2024-09-23 | ₹ 44,400 | 123182 PARWANI MOTORS | 2024-09-30 | 5000766467 | 2024-09-26
1000063865 | 2024-02-10 | Studs | 26 items | ₹ 402,950 | OPEN | Planning | [6 empty] | 4500080723 (15 items) | 2024-12-17 | ₹ 100,896 | 104373 IMPEX INDIA | 2024-12-30 | 5000782230 | 2024-12-18
1000064440 | 2024-02-03 | Cables | 8 items | ₹ 2,307,160 | OPEN | Planning |  | 307 | 2024-05-08 |  |  |  | 4500081989 | 2025-04-05
1000064496 | 2024-03-02 | Fittings | 33 items | ₹ 469,714 | OPEN | Planning |  | 143 | 2024-03-06 |  |  |  | 4500080259 | 2024-11-02 | ₹ 414,221 | 115924 Machine Tools Syndicate | 2025-02-13 | 5000784583 | 2024-12-30
1000067062 | 2024-03-20 | PT DPT TT | 22 items | ₹ 4,029,898 | OPEN | Planning |  | 311 | 2024-05-08 |  |  |  | 4500081090 (14 items) | 2025-01-24 | ₹ 2,590,000 | 121760 SAGE ASSOCIATES | 2025-05-08
1000067128 | 2024-03-30 | Power Supply module | 10 items | ₹ 555,466 | OPEN | Planning |  | 234 | 2024-04-03 |  |  |  | 4500080418 | 2024-11-18 | ₹ 525,833 | 123329 AADITECH SOLUTIONS | 2025-02-06 | 5000779662 | 2024-12-05
1000059360 | 2022-05-12 | Solenoid Valve | 19 no's | ₹ 3,243,559 | OPEN/GeM | Planning Cell |  | 158 | 2022-05-20 |  |  |  | 4500070438 (4 items) | 2022-08-13 | ₹ 28,919 | 104021 HARDWARE & PNEUMATICS | 2023-02-09 | 5000659660 | 2023-03-25
1000059551 | 2022-05-24 | Loop Powered Indicator | 1 no | ₹ 75,000 | OPEN/GeM | Planning Cell |  | 214 | 2022-06-08 |  |  |  | 4500071460 | 2022-10-27 | ₹ 120,050 | 107021 NAVEEN UDYOG, | 2023-04-24 | 5000646028 | 2023-01-23
1000060140 | 2022-07-14 | PT & TT | 27 no's | ₹ 5,684,583 | OPEN/GeM | Planning Cell |  | 286 | 2022-07-21 |  |  |  | 4500071247 (1 item) | 2022-10-11 | ₹ 226,947 | 109268 SIDHARATH ENTERPRISES, | 2023-04-06 | 5000687786 | 2023-08-09
1000060284 | 2022-07-22 | Ultrasonic Level Transmitter | 4 no's | ₹ 783,745 | OPEN/GeM | Planning Cell |  | 299 | 2022-07-28 |  |  |  | 4500071875 (2 no's) | 2022-11-30 | ₹ 161,186 | 122002 INSTRUMENTATION ENGINEERING AND SER | 2023-05-13 | 5000657022 | 2023-03-16
1000060644 | 2022-08-22 | Power supply module | 10 no's | ₹ 792,409 | OPEN/GeM | Planning Cell |  | 359 | 2022-08-24 |  |  |  | 4500072634 (8 items) | 2023-02-06 | ₹ 658,261 | 107021 NAVEEN UDYOG, | 2023-08-05 | 5000656745 | 2023-03-15
1000060719 | 2022-08-27 | Gasket | 27 no's | ₹ 902,605 | OPEN/GeM | Planning Cell |  | 391 | 2022-09-20
1000061121 | 2022-09-27 | Fuses | 7 no's | ₹ 139,745 | OPEN/GeM | Planning Cell |  | FC Done | 2022-10-26 |  |  |  | 4500072346 | 2023-01-12 | ₹ 51,557 | 101121 BATTERY CENTRE | 2023-07-11 | 5000656078 | 2023-03-13
1000061117 | 2022-09-27 | Cable trays | 2 no's | ₹ 125,136 | OPEN/GeM | Planning Cell |  | 81 | 2023-02-17 |  |  |  | 4500073300 | 2023-03-29 | ₹ 65,803 | 121947 SAIFEE ENTERPRISES | 2023-09-24 | 5000668946 | 2023-05-09
1000061116 | 2022-09-27 | Terminal Blocks | 2 no's | ₹ 79,337 | OPEN/GeM | Planning Cell |  | FC Done | 2022-10-26 |  |  |  | 4500072359 | 2023-01-13 | ₹ 64,589 | 107021 NAVEEN UDYOG, | 2023-07-11 | 5000657856 | 2023-03-20
1000061136 | 2022-09-28 | Lugs | 13 no's | ₹ 47,779 | OPEN/GeM | Planning Cell |  | FC Done | 2022-10-26 |  |  |  | 4500072321 | 2023-01-10 | ₹ 24,667 | 122111 CRYSTAL MECHANICALS PVT.LTD. | 2023-07-06 | 5000738361 | 2024-04-20
1000061179 | 2022-10-01 | MCB | 16 no's | ₹ 136,354 | OPEN/GeM | Planning Cell |  | FC Done | 2022-10-26 |  |  |  | 4500072276 | 2023-01-07 | ₹ 57,991 | 107021 NAVEEN UDYOG, | 2023-07-06 | 5000659262 | 2023-03-24
1000062181 | 2023-01-13 | PH and conductivity transmitters | 6 items | ₹ 1,653,541 | OPEN/GeM | Planning Cell |  | 83 | 2023-02-17 |  |  |  | 4500074294(4 items) | 2023-06-08 | ₹ 1,174,471 | 102765 EMERSON PROCESS MANAGEMENT (INDIA) | 2023-12-05 | 5000738508 | 2024-04-22
1000062200 | 2023-01-14 | Gasket | 27 items | ₹ 1,833,025 | OPEN/GeM | Planning Cell |  | 23 | 2023-02-02 |  |  |  | 4500073427 | 2023-04-05 | ₹ 948,339 | 101741 CHAMPION JOINTINGS PRIVATE LIMITED, | 2023-10-02 | 5000764652 | 2024-09-18

## 2026-27
Materials to be procured
S.No | Mat Description | Status | PR/PO
1 | Flanges
2 | Zss
3 | Torque Txr
4 | Vega LT | indented
5 | Radar LT
6 | Vega Density
7 | Media Converter
8 | BTS | indented
9 | Non Contact Temp
10 | Anemometer
11 | Reject Level LT
12 | Acid Pump Spares
13 | R-1001 Spares | indented
14 | ACME Spares
15 | IPA BW | Indented | 1000074150
16 | Newton BW | Indented | 1000074151
17 | Mobrey Ultrasonic probe
18 | Bucket wheel reclaimer spares
19 | Reclaimer boom PT
20 | Steam condensate Ball Valve
21 | Eletta Spare
22 | WiMate Spares
| 82642112660 | P&F PROXIMITY SWITCHES
| 82698001220 | available with pravin
| 82639031080 | Pressure Switch Range 0.2 to 4 kg/cm2 | 3 Nos |  | 2021
| 82639094560 | PR. SWITCH 16-160BAR 1/4"NPT 5A/230VAC | 3 Nos |  | 2021
| 82639201010 | PRESSURE SWITCH RANGE: 0-14 KG/CM2 | 3 Nos |  | 2021
| 82639112080 | PRESSURE SWITCH RANGE: 0.5- 10 BAR | 3 Nos |  | 2014
| 82639023500 | PRESSURE SWITCH. RANGE: 5.0 TO 25.0 BAR (70 - 350)(PSI), | 3 Nos |  | 2012
| 25010360430 | HP Pr Switch Feed End/Discharge End Trunion Bearing 20-100 Bar | 3 Nos | 8 Nos | 2012
| 82639202680 | Pressure Switch Range 0.2 to 2 kg/cm2 | 1 No | 2 Nos
| 82639032580 | GEARBOX OIL FILTER DP SWITCH TAG NO. 02 PDSH 806 SET POINT 2 BARS | 1 Nos | 3 Nos
| 82639207010 | PRESSURE SWITCH.RANGE: 0.5 TO 7.0 BAR (7 - 100)(PSI)) | 5 Nos | 15 Nos | 2012